## Slide 1: GEHC SDT Weekly Status Report
01/05/17

## Slide 2: Action items from previous meeting
Action item | Owner | Expected Closure Date | Status
PO for Andrey – Both GE and CG working through to get it issued on UK entity | Paul | 09-Dec-2016 | In Progress
Evaluation on the Skill matrix of SDT resources which is shared with GE. | Rohit/Chandra | 31-Dec-2016 | In Progress
Finalizing RACI matrix from CG and GE side | Chandra | TBD | On Hold
CLICK certification to few of our SDT Team members | Priya | 30-Jan-2016 | In Progress
Face to Face KT with GE, TechM and CG team | Chandra / Zach | 12- Jan-2017 | In Progress
CLICK KT to be planned with Gopi | Chandra | 12-Jan-2017 | In Progress
To have daily connect to discuss on workout session . | Rohit/Chandra/CG team | 30-Dec-2016 | Closed

## Slide 3
Health of the Engagement
Highlights
Help Needed
Closure of Andrey’s PO
Weekly Snapshot – 01/05/17
Delay in CLICK Certification closure
Delay in start of CLICK KT for Gopi
Risk / Issues / Challenges
All access / setups closed for the team
GIT HUB integration with Visual Studio completed
NA

## Slide 4
GE Trainings Completed
Self Learning
Open Issues/Action Item
Training Status – 01/05/17
N/A
Risk / Issues / Challenges
Agile Scrum Methodology
DevOps
Rally
C#, Asp.net, MVC, JQuery and SQL server
Agile testing
Agile estimation techniques
Click schedule
Six Sigma WBT Test
GE GDC Induction WBT Test
Software Security Awareness
Fundamentals of Application Security
Fundamentals of Secure Architecture
Fundamentals of Secure Development
GEHC Service Now System and CMDB Training
GEHC Service Now Incident & Problem Training
GEHC Service Now Change Mgmt. Training
GEHC IT ALM Requirements
GEHC IT ALM Test Management
N/A

## Slide 5
Highlights
Next Planned Activities
Open Issues/Action Item
To understand on the ongoing TechM Dev activities like code baseline and release planning
Transition Status – 01/05/17
N/A
Risk / Issues / Challenges
Face to Face Meeting is planned to start from 4th Jan 2017 – 12th Jan 2017
Ongoing Transition plan covering the application dev/support clarifications & Project processes.
CG SDT support team started secondary support on 26th Dec’16.
F2F Workout session draft agenda is prepared and reviewed

## Slide 6: Transition Status 01/05/17
Key Milestones
W 1
Introduction
Support
Development
GE HC Process
Face To Face KT
Secondary Support
Primary Support
We are here
Knowledge Transfer
Start of Stabilization
Code Walkthrough
W 5
W 6
W 7
W 2
W 3
W 4

## Slide 7: THANK YOU