## Slide 1: GEHC SDT Weekly Status Report
01/19/17

## Slide 2: Open Actions
Action item | Owner | Forum | Expected Closure Date | Status
Evaluation on the Skill matrix of SDT resources which is shared with GE. | Rohit/Chandra | Weekly Status | 31-Dec-2016 | In Progress
Finalizing RACI matrix from CG and GE side | Chandra | Weekly Status | TBD | On Hold
CLICK certification to four of our SDT Team members | CG Team | Weekly Status | 05-Feb-2016 | In Progress
Mobility Team or tiger team to be formed to resolve all CLICK mobile issues | Rohit | Jan’ 17 Workout | 20-Jan-2016 | Open
Performance issues: SDT Booking and Architecture Assessment. | Hita/Andrey | Jan’ 17 Workout | TBD | In Progress
Working on OpMech(Communication Plan & Escalation matrix) | Saraswathi/Sathyaraj | Jan’ 17 Workout | 20-Jan-2016 | In Progress
Ownership on Tickets/Process adherence(Agile Mechanism) | Suvarna/Sathyaraj | Jan’ 17 Workout | Ongoing | In Progress
Release management(Deployment activities for Release 1.3) | Jayesh/Tejashree | Jan’ 17 Workout | 03-Feb-2017 | In Progress
GEHC to find a problem manager from GE corporate | Chandra | Jan’ 17 Workout | TBD | Open
GEHC to share nonfunctional requirements | Chandra | Jan’ 17 Workout | TBD | Open
GEHC to check and confirm on L1 support - on call support | Chandra | Jan’ 17 Workout | TBD | Open
GE AVS scan report to be shared | Rohit | Jan’ 17 Workout | TBD | Open

## Slide 3
Health of the Engagement
Highlights
Help Needed
VPN token for Gopi M and Farhan
Need discussion with Tech M on code change w.r.t R1.3
Weekly Snapshot – 01/19/17
Delay in Siebel access may lead to delay in testing for Release
Delay in Click DB access(Prod, Stage, Sandbox) for Gopi, Preeti may lead to delay in resolution of incidents
Multiple open defects from testing – could lead to quality issues
Risk / Issues / Challenges
Baselined the code(R1.2) with hard testing, modified code for Release 1.3 identified and deployed locally
Successful CLICK Master data load
Primary support on from 2nd Jan’17
F2F Workout session completed successfully
Incident and Release Manager were identified
GREEN

## Slide 4: Focus Area Updates
Focus Areas | Owner | Status | Comments
Mobile Sync Issues | CG Team | In Progress | Service Now tickets raised for tracking Weekly call scheduled with CLICK team Patch 9 deployed – Sync Issue AM/PM Issue resolved
Booking SDT Performance Issues | CG Team | In Progress | Analyzed the session variables which can be moved to config file Hard coded values w.r.t CLICK can be moved to config file
Release Management | CG Team | In Progress | Release 1.3 branch created in GIT HUB Release check list preparation in progress
Incident Management | CG Team | In Progress | Incident manager identified Streamlining incidents w.r.t CLICK support cases Problem ticket creation process finalized
Support and Development Process streamlining | CG Team | In Progress | Daily SCRUM calls initiated and actions tracked to closure

## Slide 5: Incident Update
Chart: Incident Tickets
| Awaiting 3rd Party | Resolved | Resolved – Awaiting Problem | Validation and Closure
Total | 7 | 2 | 5 | 1
Chart: Problem Tickets
| Known Error / Pending CA | Open
Total | 1 | 2
Awaiting third party –category is with CLICK and TRACE DB
7 SDT Schedule / Mobile Issues
  6 - CLICK Mobile sync
  1 - TRACE DB, missing FSE data in Master file
Inferences

## Slide 6: Incident Tickets
Incident Management |  |  |  | 
Ticket # | Module | Keyword | Status | Problem #
INC1371682 | SDT Booking | Google API | Resolved – Awaiting Problem | PRB0045855
INC1389372 | SDT Booking | Google API | Resolved – Awaiting Problem | PRB0045855
INC1357120 | SDT Booking | Google API | Resolved – Awaiting Problem | PRB0045855
INC1409263 | SDT Schedule | Rule Violation | Resolved | NA
INC1399196 | SDT Schedule | Master Data | Resolved | NA
INC1370193 | SDT Mobile | Mobile Sync | Awaiting 3rd Party | NA
INC1418668 | SDT Schedule | Master Data | Awaiting 3rd Party | NA
INC1415878 | SDT Mobile | Mobile Sync - Patch 9 | Validation and Closure | NA
INC1420698 | SDT Schedule | Scheduled - Known Error | Awaiting 3rd Party | NA
INC1285226 | SDT Booking | Email Activity | Resolved – Awaiting Problem | PRB0045556
INC1310582 | SDT Booking | Performance - Connectivity | Resolved – Awaiting Problem | PRB0045475
INC1435230 | SDT Mobile | Mobile Sync | Awaiting 3rd Party | NA
INC1435245 | SDT Mobile | Mobile Sync | Awaiting 3rd Party | NA
INC1435289 | SDT Mobile | Mobile Sync | Awaiting 3rd Party | NA
INC1435961 | SDT Mobile | Mobile Sync | Awaiting 3rd Party | NA
Problem Management |  |  |  | 
Ticket # | Module | Keyword | Status | 
PRB0045855 | SDT Booking | Google API | Open | 
PRB0045556 | SDT Booking | Email Activity | Open | 
PRB0045475 | SDT Booking | Performance - Connectivity | Known Error / Pending CA | 

## Slide 7: The Team
 | Program Manager | Priya Patra
 | Solution Architect | Andrey Reiner
 | Project Manager | Saraswathi Nagaraj
 | Business Analyst/Incident Manager | Sathyaraj Rajasekar
 | Scrum Master | Suvarna Dmello
CLICK | CLICK SME | Gopi M
 | CLICK SME | Preeti Sagar
DevOps Team | Technical Lead | Hita Soni
 | SDT Architecture | Farhan Husain Syed
 | Configuration Manager | Tejashree Bhagat
 | Release manager | Jayesh Soni
 | Senior .NET Developer | Prajna Monappa
 | .NET Developer /Testing Spoc | Ebaad Chowdhry
 | .NET Developer | Deepak Vishwakarma

## Slide 8: THANK YOU