## Slide 1: GEHC SDT Weekly Status Report
02/09/17

## Slide 2: Open Actions
Action item | Owner | Forum | Expected Closure Date | Actual Closure Date | Owner Comment | Status
CLICK certification to four of our SDT Team members | CG Team | Weekly Status | 05-Feb-2017 |  | Deepak-CS & CM Jayesh-CS & CM Ebaad-CS | In Progress
Mobility Team or tiger team to be formed to resolve all CLICK mobile issues | Rohit | Jan’ 17 Workout | TBD |  |  | In Progress
Performance issues: SDT Booking and Architecture Assessment. | Hita/Sharan | Jan’ 17 Workout | 09-Feb-2017 | 09-Feb-2017 | Presentations on assessment have been scheduled on 9th Feb 11:30AM | Closed
Ownership on Tickets/Process adherence(Agile Mechanism) | Suvarna/Sathyaraj | Jan’ 17 Workout | Ongoing |  |  | In Progress
Release management(Deployment activities for Release 1.3) | Jayesh/Tejashree | Jan’ 17 Workout | 03-Feb-2017 |  | Deployment would takes place on 11-Feb-2017 | In Progress
GEHC to find a problem manager from GE corporate | Chandra | Jan’ 17 Workout | TBD |  | Will identify the problem manager when we have problem in hand. | On Hold

## Slide 3: Open Actions (contd.)
Action item | Owner | Forum | Expected Closure Date | Actual Closure Date | Owner Comment | Status
GEHC to share nonfunctional requirements | Chandra | Jan’ 17 Workout | TBD |  | Few are identified from Rally | In Progress
GEHC to check and confirm on L1 support - on call support | Chandra | Jan’ 17 Workout | TBD |  | To confirm on L1 support | In Progress
Analysis and fixing of defects raised by Testing team and Business users. | CG Dev | Defect triage | 11-Feb-2017 |  |  | In Progress

## Slide 4
Health of the Engagement
Highlights
Help Needed
VPN token for Gopi M
Weekly Snapshot – 02/09/17
Click DB access(Prod, Stage, Sandbox) for Gopi & Preeti
Risk / Issues / Challenges
7 open defects from UAT and 2 defects from testing team have been closed. 4 open defects are awaiting business confirmation
User stories are created and shared with business for confirmation. Grooming in progress
Sprint planning was done. User Stories are broken down to tasks and estimations are made.
On SDT architecture assessment, proposed solutions for improving performance. Prepared plan for its implementation
Successful CLICK Master data load in Production
Deployment of R2.1.0 (Click related) testing completed on Sandbox1
Deployment of R1.3 in staging is completed and UAT is completed
GREEN

## Slide 5: Focus Area Updates
Focus Areas | Owner | Status | Comments
Mobile Sync Issues | CG Team | In Progress | All reported issues related to Mobile sync are captured and analyzed. Findings was shared with business. 5 issues were fixed from click and will be a part of Patch9/10. Monitoring in progress
SDT Booking Performance Issues | CG Team | In Progress | User story was created and is in Rally. Further assessment on SDT Booking tool was done and shared Estimations and timelines have been shared
Release Management | CG Team | In Progress | Release check list was created and it will be updated in our Release readiness check call.
Incident Management | CG Team | Ongoing | Streamlining incidents w.r.t CLICK support cases Problem ticket creation process finalized. Incidents reported in this week are closed.
Support and Development Process streamlining | CG Team | Ongoing | Daily SCRUM calls initiated and actions tracked to closure Ensuring all email communication to have incident ticket created. Internal defect tracker is maintained to track the QA/UAT defects and owners defined for each defect.

## Slide 6: Incident Update
Resolved 2 incident tickets and provided findings for 3 incident tickets
17 Awaiting 3rd party - SDT Schedule / Mobile Issues
  15 - CLICK Mobile issues
  1 - Known error/issue
  1 - Master Data
Inferences
Chart: Problem tickets
| Known Error / Pending CA | Open
Total | 1 | 2
Chart: Incident tickets
| Awaiting 3rd Party | Awaiting User Info | Closed | Resolved | Resolved – Awaiting Problem
Total | 17 | 3 | 7 | 2 | 2

## Slide 7: Incident Tickets
Incident Management |  |  |  | 
Incident # | Module | Key Words | Status | Problem #
INC1370193 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1418668 | SDT Schedule | Master Data | Awaiting 3rd Party | NA
INC1420698 | SDT Schedule | Scheduled - Known Error | Awaiting 3rd Party | NA
INC1435230 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1435245 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1435289 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1435961 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447060 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447037 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447031 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1446914 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447042 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447028 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1454094 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1463913 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1464027 | SDT Booking | Click Issue | Awaiting User Info | NA
INC1477114 | SDT Booking | Mobile Sync Issue | Awaiting User Info | NA
INC1480047 | SDT Mobile | Mobile Validation Issue | Awaiting 3rd Party | NA
INC1480941 | SDT Mobile | Mobile Validation Issue | Awaiting 3rd Party | NA
INC1480772 | SDT Mobile | Mobile sync Issue | Awaiting User Info | NA
Problem Management |  |  |  | 
Problem # | Module | Keyword | Status | Incident #
PRB0045855 | SDT Booking | Google API | Open | INC1371682, INC1389372, INC1357120
PRB0045895 | SDT Booking | Email Activity | Open | INC1285226
PRB0045475 | SDT Booking | Performance - Connectivity | Known Error / Pending CA | INC1310582

## Slide 8: The Team
 | Program Manager | Priya Patra
 | Solution Architect | Andrey Reiner
 | Project Manager | Saraswathi Nagaraj
 | Business Analyst/Incident Manager | Sathyaraj Rajasekar
 | Scrum Master | Suvarna Dmello
CLICK | CLICK SME | Gopi M
 | CLICK SME | Preeti Sagar
DevOps Team | Technical Lead | Hita Soni
 | SDT Architecture | Farhan Husain Syed
 | Configuration Manager | Tejashree Bhagat
 | Release manager | Jayesh Soni
 | Senior .NET Developer | Prajna Monappa
 | .NET Developer /Testing Spoc | Ebaad Chowdhry
 | .NET Developer | Deepak Vishwakarma

## Slide 9: THANK YOU