## Slide 1: GEHC SDT Weekly Status Report
04/19/17

## Slide 2: Open Actions
Action item | Owner | Forum | Expected Closure Date | Actual Closure Date | Owner Comment | Status
Mobility Team or tiger team to be formed to resolve all CLICK mobile issues. | Rohit/Gopi | Jan’ 17 Workout | TBD |  | On monitoring the debug logs: No Issues reported | In Progress
Performance issues: SDT Booking and Architecture Assessment. | Hita/Andrey/Urmila/Chandra | Jan’ 17 Workout | 28-Feb-2017 |  | Development of Logging tool has been enhanced which includes Code for logging IP addresses, Click request and Response. | In Progress
Ownership on Tickets/Process adherence(Agile Mechanism) | Suvarna/Sathyaraj | Jan’ 17 Workout | Ongoing |  |  | In Progress
GEHC to check and confirm on L1 support - on call support | Chandra/CG | Jan’ 17 Workout | TBD |  | No services available in ServiceNow tool. Exploring other opportunities | In Progress

## Slide 3
Health of the Engagement
Highlights
Help Needed
Need clarity on the responses received related to timing / frequency of backup, patches and domain policies on server infrastructure related queries - Chandra
Weekly Snapshot – 04/19/17
Issues in comprehending data flow due to unavailability of CLICK environment details - Rohit
Unavailability of MT analyzer tool access will lead to difficulties in viewing of messages (Request & Response) for all the CLICK environment – Chandra
Issues in the CRP environment may impact current sprint user stories testing process - Chandra
Risk / Issues / Challenges
GREEN
The CLICK deployment of Release 2.3.0 on Staging has been done successfully.
Deployment of Release 2.3 for EU templates was done successfully on SB3
  Weekly Master data uploaded successfully
  Development of all performance related user stories marked for this current sprint are completed.
  Accurate display of error messages of SDT and Web client has been implemented.
  Validation implemented for part tool details form fields such as address, postal code and city so that user can not add illegal characters in the mentioned text boxes.
  Test script creation for functional user stories and integration testing is in progress.

## Slide 4: Focus Area Updates
Focus Areas | Owner | Status | Comments
Mobile Sync Issues | CG Team | In Progress | Yet to receive end to end environments details from CLICK team denied due to policy reasons Connected with business user for issues reported in debug log) :No issues reported till now.
SDT Booking Performance Issues | CG Team | In Progress | Bumping functionality is removed from the SDT booking code. Date format sync in appointment slots page has been completed. Implemented code changes to read SR 'NEW' status from Siebel instead of Click.
Release Management | CG Team | Ongoing | Release check list was created and it is updated in our Release readiness check call.
Incident Management | CG Team | Ongoing | Streamlining incidents w.r.t CLICK support cases Problem ticket creation process finalized. Incidents reported in this week are closed.
Support and Development Process streamlining | CG Team | Ongoing | Agile metrics identified and tracked through Rally. Ensuring all email communication to have incident ticket created. Internal defect tracker is maintained to track the QA/UAT defects and owners defined for each defect.

## Slide 5
Health of the Egagement
Release 2 –Iteration 4 highlights
Help Needed
Weekly Snapshot & Agile Metrics – SDT Development
  SDT Iteration 3 -(03/21/2017 -03/31/2017) -Completed
  SDT Iteration 4 -(04/05/2017 -04/19/2017 –In progress
Release 2
Risk / Issues / Challenges
Iteration 4 Burndown chart
  Committed User Stories for Iteration 4 :12
    Technical user stories:3
    Spike user stories:2
    Functional user stories:8
  Implementation Done for all user stories
  Test case creation done for all user stories
  Deployment is done for 4 completed user stories in CRP.
  Testing –In progress for completed user stories in local environment as CRP is down.
  Defects are tracking through rally.
Iteration 4 Defect by State

## Slide 6: Agile Metrics - Support
Iteration Support Burndown Chart:
Support activities keep on added up on a daily basis based on the support tickets that we receive. Hence there’s a mismatch with ideal.
End of the sprint, all tickets are closed and all the user stories are accepted by Product owner.
Iteration Cumulative Flow Diagram
The tasks related to Release 2.3 and ES LS popup issue, Mobile Sync issues and 1 Incident are in completed..
All the Incidents are completed.
3 incidents are in progress for awaiting 3rd party approval are moved from Iteration 5 to 6.
Inferences
Support Iteration 5 (04/03/2017 - 04/14/2017)
Burndown chart
Cumulative Flow Diagram

## Slide 7: Agile Metrics – SDT Booking Velocity Chart
SDT
Velocity Chart
SDT Iteration 1
  Velocity of team:50 story points
  Accepted By PO: 13 story Points
  US85 and US 97 –Accepted by PO as these user stories are already deployed in production as part of release 1.3.1
  Iteration length: 10 days(2 weeks)
SDT Iteration 2
  Velocity of team: 9 story points
  Accepted By PO: 9 story Points
  Iteration length: 5 days(1 week)
SDT Iteration 3
  Velocity of team: 20 story points
  Accepted By PO: 17 story Points
  Iteration length: 8 days
Inferences
Chart: 
| SDT Iteration 1(02/14/2017 - 02/27/2017) | SDT Iteration 2(03/06/2017 - 03/10/2017) | SDT Iteration 3(03/21/2017 - 03/31/2017)
Velocity(Story Points) | 50 | 9 | 20
Accepted By PO(SPs) | 13 | 9 | 17

## Slide 8: Agile Metrics – Support Velocity Chart
Support
Support Iteration 1
  Velocity of team:5 story points
  Accepted By PO: 5 story Points
  Iteration length: 8 days
Support Iteration 2
  Velocity of team:20 story points
  Accepted By PO: 19 story Points
  Iteration length: 12 days
Support Iteration 3
  Velocity of team:20 story points
  Accepted By PO: 20 story Points
  Iteration length: 11 days
Support Iteration 4
  Velocity of team:17 story points
  Accepted By PO: 17 story Points
  Iteration length: 11 days
Support Iteration 5
  Velocity of team:20 story points
  Accepted By PO: 12 story Points
  Iteration length: 10 days
Inferences-Velocity Chart
Chart: 
| Support Iteration 1(02/01/2017 - 02/10/2017) | Support Iteration 2( 2/13/2017 - 2/28/2017) | Support Iteration 3(03/01/2017 - 03/15/2017) | Support Iteration 4(03/16/2017 - 03/31/2017) | Support Iteration 5 (04/03/2017 - 04/14/2017)
Velocity(Story Points) | 5 | 20 | 20 | 17 | 20
Accepted By PO(SPs) | 5 | 19 | 20 | 17 | 12

## Slide 9: Agile Metrics – Resource Utilization
Weekly resource Utilization(5th Apr 2017 – 19th Apr 2017)
Chart: 
| Hita Soni | Farhan Hussain | Tejashree Bhagat | Jayesh Soni | Ebaad Chowdhry | Deepak Vishwakarma | Prajna Monappa | Sathyaraj Rajasekar | Gopi Mottai | PreetiSagar Godi | Saraswathi Nagaraj | Suvarna Dmello | Urmila Gumata | Binu Mohan | Ramesh, Dhivyabharathi
Total Available Hrs per Sprint Hrs | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 64 | 64 | 88 | 80 | 88 | 88 | 72 | 80
Hours Spent on Sprint Ceromonies in (%) | 18.125 | 18.125 | 18.125 | 18.125 | 18.125 | 18.125 | 18.125 | 20.3906 | 18.125 | 18.125 | 19.9375 | 18.125 | 18.125 | 18.125 | 18.125
Ge meetings/Emails in (%) | 30.625 | 31.25 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 25.5682 | 36.3636 | 31.25 | 25 | 34.375 | 18.125 | 20.4545 | 17.0455
Support (%) | 0 | 1.1364 | 25 | 25 | 0 | 31.25 | 12.5 | 42.1875 | 31.875 | 22.7273 | 0 | 0 | 17.0455 | 0 | 11.25
Hrs Spent on Iteration 4 (%) | 48.8636 | 47.7273 | 36.3636 | 40.9091 | 68.1818 | 29.5455 | 50 | 9.375 | 7.8125 | 27.2727 | 52.5 | 45.4545 | 45.4545 | 58.3333 | 48.75
Total(%) | 98 | 98 | 92 | 97 | 99 | 91 | 93 | 98 | 94 | 99 | 97 | 98 | 99 | 97 | 95

## Slide 10: Incident Update
Resolved 6 incident ticket
3 Incidents got closed
15 Awaiting 3rd party - SDT Schedule / Mobile Issues
2 Awaiting User Info
Inferences
Chart: Incidents from 12/04/2017 to 18/04/2017
| Awaiting 3rd Party
Count of Number Total | 3
Chart: Cumulative Incidents
| Active | Awaiting 3rd Party | Awaiting User Info | Closed | Resolved | Resolved – Awaiting Problem | Grand Total
Count of Number Total | 1 | 15 | 2 | 65 | 6 | 2 | 91
Chart: Incident's Resolved/Closed this Week
| Resolved | Closed
Total | 6 | 3

## Slide 11: Incident Tickets
Incident Management |  |  |  |  |  | 
Incident # | Module | Key Words | Priority | Status | Location | Queue wait time
INC1735928 | SDT Schedule | Click Issue | 4 - Low | Awaiting 3rd Party | ASPAC-South Korea-Seoul | a month ago
INC1736222 | SDT Schedule | Click Issue | 4 - Low | Awaiting 3rd Party | ASPAC-India-Bangalore | a month ago
INC1738700 | SDT Module | Click Issue | 3 - Moderate | Awaiting 3rd Party | ASPAC-India-Bangalore | a month ago
INC1747182 | SDT Mobile | Click Issue | 3 - Moderate | Awaiting 3rd Party | ASPAC-India-Bangalore | 30 days ago
INC1754593 | SDT Module | Click Issue | 5 - Request for Service | Awaiting 3rd Party | ASPAC-India-Bangalore | 28 days ago
INC1766606 | SDT Module | Mobile Sync Issue | 3 - Moderate | Awaiting 3rd Party | ASPAC-India-Bangalore | 21 days ago
INC1777886 | SDT Module | Click Issue | 3 - Moderate | Awaiting 3rd Party | EMEA-Israel-Haifa | 17 days ago
INC1779626 | SDT Module | Click Issue | 3 - Moderate | Awaiting 3rd Party | ASPAC-Malaysia-Wilayah Persekutuan | 16 days ago
INC1793968 | Click | Click Issue | 5 - Request for Service | Awaiting 3rd Party | ASPAC-Malaysia-Wilayah Persekutuan | 11 days ago
INC1477114 | SDT Booking | Mobile Sync Issue | 4 - Low | Awaiting User Info | ASPAC-South Korea-Seoul | 1 months ago
INC1480772 | SDT Mobile | Mobile sync Issue | 4 - Low | Awaiting User Info | ASPAC-South Korea-Seoul | 1 months ago
INC1816304 | SDT Module | SDT Booking issue | 5 - Request for Service | Awaiting 3rd Party | EMEA-Israel-Haifa | 13 days ago
INC1825858 | SDT Module | SDT Booking issue | 3 - Moderate | Awaiting 3rd Party | ASPAC-South Korea-Seoul | 8 days ago
INC1825781 | Click | Click Issue | 4 - Low | Awaiting 3rd Party | ASPAC-South Korea-Seoul | 8 days ago
INC1831431 | Click | Click Issue | 1 - Critical | Awaiting 3rd Party | ASPAC-Malaysia-Wilayah Persekutuan | 6 days ago
INC1831436 | Click | Click Issue | 1 - Critical | Awaiting 3rd Party | ASPAC-Malaysia-Wilayah Persekutuan | 6 days ago
INC1840513 | Click | Click Issue | 2 - High | Awaiting 3rd Party | ASPAC-Malaysia-Wilayah Persekutuan | Today
Problem Management |  |  |  |  |  | 
Problem # | Module | Keyword | Status |  |  | Incident #
PRB0045855 | SDT Booking | Google API | Closed |  |  | INC1371682, INC1389372, INC1357120
PRB0045475 | SDT Booking | Performance - Connectivity | Known Error / Pending CA |  |  | INC1310582

## Slide 12: THANK YOU