## Risk and Mitigation Plan
Risk and Mitigation Plan
Risk Identification |  |  | Risk Priortization |  |  |  | Risk Communication | Risk Mitigation | Risk Tracking |  |  |  | Revised Risk Priortization
Identification Date | Identified Risk | Possible Impact(s) | Probability of Occurrence | Detectability of Risk | Severity of Impact | RPN (Criticality) | Stakeholders Impacted and Communicated | Mitigation Initiative(s) | Status | Responsibility | Closure Date | Days Taken | Probability of Occurrence | Detectability of Risk | Severity of Impact | RPN (Criticality)
2017-01-09 | Preparing Dev env. for defect fixing(INT CRP second instance, Dev2, Sandbox2) | Delay defect fixing, replication of defects | 2 | 2 | 4 | 16 |  | Setup of a backup env for bug fixing/Need to do the bug fixes in GITHUB branch | Not Started | Jayesh
2017-01-16 | Dependency on Click team - Get click DB access | Adherence to SLAs | 2 | 1 | 4 | 8 |  | Debugging thru'SXP and log files | Not Started | Gopi
2017-01-30 | Resources in shifts: Check on GE L1 support | Communication gap/Impact in productivity | 3 | 1 | 2 | 6 |  | Deploying resources in Night and early morning shifts | 50% | Saraswathi
2017-02-06 | Delay in Product Backlog grooming | Impact in sprint planning and estimations | 2 | 1 | 4 | 8 |  | User Story to be defined by CG team and sent to Business users for confirmation | 25% | Sathyaraj
2017-02-13 | Dependency on CLICK and infrastructure to resolve Performance issues in SDT | Impact on usage of application and customer satisfaction | 3 | 1 | 4 | 12 |  | Depend on Log files for analysis | 35% | Hita/ Andrey
Total RPN (Criticality) (Category-wise) | [5 empty] | 34 | [9 empty] | 0
Note on B7: Available source of Risk Identification: Input and Process in SIPOC Proposal/ Contract Customer Communication Proposal Assumptions Estimation Assumptions Known Project Constraints Project Analysis Reports of Past Projects
Note on I7: Communicate Risks as below If color of RPN (Criticality) Box is : Red 1. Customer, as appropriate 2. Project Leadership Team 3. Appropriate Function Heads 4. Quality Manager/ Facilitator 5. Key Resources in Project Yellow 1. Project Leadership Team 2. Appropriate Function Heads 3. Quality Manager/ Facilitator 4. Entire Project Team Blue 1. Quality Manager/ Facilitator 2. Entire Project Team
Note on E8: 1 = Improbable 2 = Probable 3 = Very Likely
Note on F8: 3 = Difficult to Detect 2 = Moderately difficult to detect 1 = Easy to Detect
Note on G8: 8 = Catastrophic 4 = Critical 2 = Marginal 1 = Negligible
Note on H8: Risk Priortization Number (RPN) = Probability X Detectability X Severity
Note on O8: 1 = Improbable 2 = Probable 3 = Very Likely
Note on P8: 3 = Difficult to Detect 2 = Moderately difficult to detect 1 = Easy to Detect
Note on Q8: 8 = Catastrophic 4 = Critical 2 = Marginal 1 = Negligible
Note on R8: Risk Priortization Number (RPN) = Probability X Detectability X Severity