## Project Profile
GEHC SDT Knowledge Transition Plan
Opportunity Id | NA
Opportunity Name | GE Healthcare SDT Transition
Prepared/Modified by | Role | Date of Preparation
Krishna Chaitanya Pabolu Venkata | Transition Manager | 2016-11-16
Reviewed by | Role | Date of Review
Handa, Rohit | Sr Technical Project Manager
Approved by | Role | Date of Approval
Waltz, Zachary | ITLP
Circulation List | GEHC SDT Team, TechM & CG SDT Teams | Version Number of the template: 1.2
Version Number | 1

## Read Me
READ ME
KT Plan Team Members
Fill in the Project details : Project ID, Project Name, Old Team Member, New Team Member, Overlap Period
Initial Approval is required at the start of the KT. Manager has to sign off with date
Team Member has to fill status of the components, Hours required, Start date, End Date, Risks and comments
Components description is given below the table.Team can add points specific to the project.
Coloumns with * are mandatory to fill.
Person giving KT, Person receiving KT and Manager have to sign off the Plan on completion
Please slelect the applicability of each row item in component table based on the role to be played by new resource.
Deliverables Handover
Any deliverable which the Person giving KT handovers to the person receiving KT will be added in this sheet
Sign off from both the person giving KT and person receiving KT is required
Handover for CM
If the Person is the CM of the Project, he/she has to give CM handover to person receiving KT as well.
Sign off from both the person giving KT and person receiving KT is required

## GEHC SDT KT Plan
Customer Name* | GE Healthcare |  | Project Name* |  | SDT Transition
New vendor Name* | Capgemini India |  | Old vendor Name* |  | TechMahindra
Component | Status* | Hours Required* | Pitcher | Start Date* (mm/dd/yy) | End Date* (mm/dd/yy) | Risks (If any) Optional | Comments Optional
Project Planning Activities | Completed | 4 | Rohit / Chandra | 2017-12-01 | 2017-01-09
Project Monitoring Activities | Completed | 4 | Rohit / Chandra | 2017-01-04 | 2017-01-09
Application Knowledge to Practice | Completed | 35 | Rajesh / Joy | 2016-12-01 | 2016-01-31
Database Handling | Completed | 2 | Rohit / Chandra | 2017-01-04 | 2017-01-09
Application Support Knowledge to Practice | Completed | 25 | Martand / Debashis | 2016-12-01 | 2016-12-23
Incident/Problem/Change Management | Completed | 4 | Rohit / Chandra | 2017-01-04 | 2017-01-09
GxP/ Non GxP Processes | Completed | 4 | Rohit / Chandra | 2017-01-04 | 2017-01-09
Document Walkthrough | Completed | 4 | Chandra/Satyapal Kiran | 2017-01-04 | 2017-01-23
Project End Activities | Completed | 4 | Srini / Martand | 2017-01-04 | 2017-01-09
General Activities | Completed | 8 | Chandra/Srini | 2017-01-04 | 2017-01-09
Face to Face Work out sessions | Completed | 40 | SDT Teams | 2017-01-04 | 2017-01-09
TechM Primary/ CG secondary Support | Completed | 40 | Saraswathi & Team | 2016-12-26 | 2017-01-06
CG Primary/ TechM Secondary Support | Completed | 40 | Saraswathi & Team | 2017-01-02 | 2017-01-13
TOTAL Knowledge Transfer Effort Required (in hours) |  | 214
Overall Start/End Dates |  |  |  | 2016-12-01 | 2017-01-23
|  | Name* |  | Date Signed* (mm/dd/yy)
KT Plan (initial approval) | Transition Manager/Supervisor | Krishna Chaitanya Pabolu Venkata |  | 2016-11-30
Overall KT Process | Person Giving KT | Srinivas Divi
Completion | Person Receiving KT | Saraswathi Nagaraj
(sign-off) | Manager/Supervisor | Patra, Priya
Component Table
Component | Description |  | Pitcher | Applicability* Y/N | Current Status* | Start Date | End Date | Comments
Project Planning Activities | Work Allocation |  | Rohit / Chandra | Y | Completed | 2016-12-01 | 2016-12-01 | Agile Method of project execution with Rally Tool for project deliverables - Invoice is based on Rally user stories
| Technical Know-how of the project |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Details of bug tracking software/tools being used |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Information about test schedule |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Tools used for testing/development/maintenance/support |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Test data Creation/Test Procedures |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Details of s/w and h/w provided |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Location of media and manual |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Contact Persons - Telephone No., Extension No., Fax No. |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| List of documents/e-mails to be sent. |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Conference calls to be made or attended. |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Source Control and version control |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Naming conventions and Programming Language standards used from QMS |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Details of Controlled and Uncontrolled documents |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Backup Procedures |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
Project Monitoring Activities | Next milestones |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Time sheets status |  | n/a | N | Not Applicable
| Mistakes, pitfalls, delays that have happened and corrective actions initiated |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Customer specific complaints |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-19
| Information about the team members |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Team member previous history |  | Rohit / Chandra | N | Not Applicable
| Whether existing deadlines are met |  | Rohit / Chandra | N | Not Applicable
| What has already been delivered |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Problems encountered during testing |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Any more time is required or delays expected |  | Rohit / Chandra | N | Not Applicable
| Formal methods of delivery done |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Correspondence & action taken on pending issues |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Records of Installation/ Commissioning, Breakdown / Maintenance ... etc. |  | Rohit / Chandra | N | Not Applicable
Application Knowledge to Practice | Functional Know-how of the Application |  | Demo (Sitara / Paul) or Anil / Vinay | Y | Completed | 2016-12-01 | 2017-01-19 | Anil will cover this topic in coming week 20-Dec: Anil covered the Siebel access 6-Jan : VPT PPT has to be understood Recording session from Manjula on Click/ Functional knowldge to be understood Presentation will be held, after assessment we will mark this complete
Smart Dispatch Tool[SDT] | Technical Know-how of the Application |  | Rajesh | Y | Completed | 2016-12-01 | 2016-12-06 | 6-Jan : Presentation will be held, after assessment we will mark this complete
Visual Planning Tool[VPT] | Overview of Architecture, data flows etc., |  | Rajesh / Joy | Y | Completed | 2016-12-01 | 2016-12-06
SDT Mobile App | Business use cases walkthrough |  | Vinay / Anil (demo) | Y | Completed | 2016-12-01 | 2017-06-01 | Rally use stories discussion is in progress
SIEBEL, SMAX and FDA validation | Application Metadata |  | N/A | N | Not Applicable
TRACE application and CLICK software | Functional & Technical use case walkthrough |  | Rajesh / Joy | Y | Completed | 2016-12-01 | 2016-12-06 | Access to Siebel for CG team is still open
Application Protocals & Interfaces | Knowledge on Upstreams, downstream and depencies |  | Rajesh / Joy | Y | Completed | 2016-12-01 | 2016-12-06 | Middleware team to cover the specifics 16-Dec: Planned for 19-Dec 2nd half session~
| Code version controls and schedulings |  | Chandra | Y | Completed | 2016-12-06 | 2017-01-31 | Saraswathi to co-ordinate with Chandra and proceed with next steps 6-Jan : Modified/changed code files for the SDT 1.3 version to be received by Rajesh/Joy 23-Jan-2017: As per Saraswathi Compared from V1.2 and captured the changed files As per CM comments, the CG team has taken version 1.3 as baseline Saraswathi to validate with team and confirm for the item closure. 31-jan-2017: Team has taken Version 1.3 as baseline and action item can be closed.
| Adhoc/ One-time / History conversions/load walkthrough |  | Prosenjit/Gopi | Y | Completed | 2017-01-05 |  | 16-Dec: Manual process for weekly load to Click 6-Jan : Gopi to perform weekly load and confirm the process
| Technology stack like tools etc., |  | Martand | Y | Completed | 2016-12-01 | 2016-12-16
| Testing procedures & environment setup walkthrough |  | Rajesh / Joy | Y | Completed | 2017-01-06 | 2017-01-06 | Kannan would be the right contact to cover this topic - Validate it with Chandra 16-Dec : Once the ALM access is completed, the session will continue after that
| Known issues & planned fixes |  | Martand | Y | Completed | 2016-12-05 | 2016-12-16
| Lesson Learnt & Best practices followed |  | Vinay / Anil / Martand | Y | Completed | 2017-01-06 | 2017-01-06 | 19-Dec: Martand commented that this topic would be covered by Chandra/Rohit 6-Jan : Rohit will share document
| Document, GE Box & MWS walkthrough |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 16-Dec : Team to ensure the required access to these documents are enabled. MWS upload access to needy team members
| Known Risk functionalities |  | Martand | Y | Completed | 2016-12-08 | 2016-12-08
| If any missed etc., Code Walkthrough |  | Rajesh / Joy | Y | Completed | 2016-12-06 |  | As suggested by Chandra, the code modules walkthrough is needed
| Clarifications |  | Rajesh / Joy | Y | Completed | 2016-12-06
Database Handling | DB Overview |  | Rahul | Y | Completed | 2017-01-05 | 2017-01-05 | 16-Dec: Need additional DB Developer apart from Haritha ?
| How to create objects in libraries |  | N/A | N | Not Applicable
| Giving grant access to the User |  | N/A | N | Not Applicable
| Environment walkthrough like Test, UAT, QA etc., |  | N/A | N | Not Applicable
| Validation & verification process followed |  | N/A | N | Not Applicable
| Database space & limitations overview |  | N/A | N | Not Applicable
| Clarifications |  | N/A | N | Not Applicable
Application Support Knowledge to Practice | Functional Know-how of the Application |  | Demo (Sitara / Paul) or Anil / Vinay | Y | Completed | 2016-12-01 | 2017-01-06 | Anil will cover this topic in coming week 20-Dec: Anil covered the Siebel access 6-Jan : Closed in F2F
| Technical Know-how of the Application |  | Rajesh | Y | Completed | 2016-12-01 | 2017-01-06 | Code working on IDE would be DoD
| Knowledge on Upstreams, downstream and depencies |  | Rajesh / Joy | Y | Completed | 2016-12-16 | 2016-12-16
| Code version controls and schedulings |  | Chandra | Y | Completed | 2016-12-06 | 2017-01-06 | Saraswathi to co-ordinate with Chandra and proceed with next steps 16-Dec : Jayesh completed code setup along with GITHub Once the Visual studio setup is completed this task would be marked complete 6-Jan :
| Adhoc/ One-time / History conversions/load walkthrough |  | Prosenjit/Gopi | Y | Completed |  | 2017-01-06 | 16-Dec: Manual process for weekly load to Click 6-Jan : Master data load on weekly,
| Technology stack like tools etc., |  | N/A | Y | Completed | 2016-12-02 | 2016-12-16 | 6-Jan : Postman, visula studio, IE 11, Service now
| Testing procedures & environment setup walkthrough |  | Kannan | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan: Following GxP process, so it will be development team test environment
| History of Incidents, Problems etc., |  | Martand / Debashis/ | Y | Completed | 2016-12-03 | 2017-01-06 | Incidents, Problems completed on 12/07/2016 Chandra will be covering Change requests 6-Jan : Quick check on current open ticets Ebaad to consolidate the list and have quick discussion
| Known issues and issue fixing walkthrough |  | Martand / Debashis | Y | Completed | 2016-12-05 | 2016-12-16 | 9-Dec: CG team will document on the discussed known issues and share it with TechM support team and take the signoff on the identified issues
| Application & tickets SLA's |  | Martand / Debashis | Y | Completed | 2016-12-02 | 2017-01-06
| Daily/Weekly/Monthly/Quaterly/Annually etc., load overview & process |  | Martand / Debashis | Y | Completed | 2016-12-05 | 2017-01-06
| Middleware(MW) coordination between the Interfaces |  | Satyapal Kiran | Y | Completed | 2017-01-05 | 2017-01-05 | 6-Jan : Kiran covered on 5-Jan
| Application deployment and Start/Stop process |  | Chandra | Y | Completed | 2016-12-13 | 2017-01-06 | 6-Jan : Web COE is for validated environment. GIT Hub to dev -> stage -> production
| Status reporting |  | Martand / Debashis | Y | Completed | 2016-12-06 | 2017-01-06 | 6-Jan: Ongoing reporting
| Ticket Analysis & Status tracking on daily basis |  | Martand / Debashis | Y | Completed | 2016-12-02 | 2016-12-06
| Monthly consolidation of tickets, status & analysis |  | Martand / Debashis | Y | Completed | 2016-12-06 | 2016-12-06
| WSR reporting |  | Martand / Debashis | Y | Completed | 2016-12-06 | 2016-12-06
| Ops review process - Servicenow Graph generation for Incidents etc., |  | Srini | Y | Completed | 2016-12-06 | 2017-01-06 | 12-Dec Info to Srini to take up this session, Only leads needed
| Stakeholders & others DL's, Contacts |  | Chandra / Martand/ Rohit | Y | Completed | 2016-12-12 | 2017-01-06 | Stakeholders information to be shared by Chandra
| Working with ServiceNow tickets |  | Debashis | Y | Completed | 2016-12-02 | 2016-12-16
| Access, Support & Enhancement tickets process |  | Martand / Debashis | Y | Completed | 2016-12-06 | 2017-01-06
| Application outage process - Engage GCC |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Implemention/production deployment process & Change requests |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Outage/ application corresponding communication groups |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : During deployment process the details will be communciated
| GE service now Config items, groups etc., to manage support |  | Rohit / Chandra | Y | Completed | 2016-12-02 | 2017-01-06
| Known Risk functionalities |  | Martand / Debashis | Y | Completed | 2016-12-08 | 2016-12-08
| If any missed etc., |  |  | Y | Completed | 2016-12-02 | 2017-01-06
| Clarifications |  |  | Y | Completed | 2016-12-02 | 2017-01-06
Incident/Problem/Change Management | Overview of Servicenow |  | Rohit / Chandra | Y | Completed | 2016-12-02 | 2017-01-06
| Process of requesting access to Servicenow |  | Rohit / Chandra | Y | Completed | 2016-12-05 | 2017-01-06
| Incident Management Process |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Problem Management Process |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Change Management Process |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Will revist during the release
| Status reporting & Approval process |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Clarifications |  |  | Y | Completed | 2017-01-06 | 2017-01-06
GxP/ Non GxP Processes | Overview of Non Gxp Processes & GxP processes |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Will revist during the release
| Documentation & Approval processes |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Will revist during the release
| ALM Test case Management |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Will revist during the release
| Clarifications |  | Rohit / Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Will revist during the release
Documentation Walkthrough | MWS documents & versions Overview |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan :
| GE library/GE Box documents & versions Overview |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Application overview & flow documents |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| User requirements, design, technical, tracebility, metadata etc., |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Rally user stories(completed + Backlog) |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Application support documentation |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Refer to GE Box/MWS
| RTS/GAMS team support documentation |  | Chandra | N | Not Applicable
| Test scenarios evidences(Functional + Technical) |  | Chandra/Kannan | Y | Completed | 2017-01-06 |  | 6-Jan : Obtain access to ALM and validate 23-Jan : Satya, Hita got access to ALM and other team members will raise on the needy basis
| ALM Test case Management Overview |  | Kannan | Y | Completed | 2017-01-06 | 2017-01-06
| if any missed; |  |  | Y | Completed | 2017-01-06 | 2017-01-06
Project End Activities | Complete S/W or Application demo if required |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Details of Project Closing documents related to project closure and documents/files to be archived. |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Will revist during the release
| Delivery/Go-Live Procedure |  | Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Will revist during the release
| Details of tasks to be closed |  | Srini / Martand | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Will revist during the release
General Activities | E-Mail Messages and correspondence |  | N/A | Y | Completed | 2017-01-06 | 2017-01-06
| S/W libraries in the PC/Server |  | Chandra | N | Not Applicable | 2017-01-06 | 2017-01-06
| Source Codes/Procedures |  | N/A | Y | Completed | 2017-01-06 | 2017-01-06
| Details of Security procedure/ODC Policy followed and Maintained |  | Rohit/Chandra | Y | Completed | 2017-01-06 | 2017-01-06 | 6-Jan : Rohit to provide the list of mandatory trainings
| Notable events which took place in past |  | Rohit/Chandra | Y | Completed | 2017-01-06 | 2017-01-06
| Mandatory Process & Technical Trainings need to be attended |  | GE Exams for Application security and Service Now (ITIL) | Y | Completed | 2017-01-06 | 2017-01-06
Formulas:
SDT Transition = MAX(G9:[SDT Transition, row above])

## F2F KT Agenda
Agenda | SDT F2F Workout Session
Participants | Rohit Handa, Chandramohan Gupta, Krishna Chaitanya Pabolu Venkata, Joy Chakraborty, Rajesh Babu Kallem, Prosenjit Ganguly, Gaurav, Priya, Saraswathi, Sathyaraj, Suvarna, Jayesh, Ebaad, Krishna, Andrey, Gopi, Vamsi, Vivek, Ashish, Anil, Haritha
Workout Session | Date | Time Slots | Topics | Pitcher | Comments | Status
| 2017-01-04 | 10:00 AM - 12:00 PM | SDT Functional Overview | Rajesh Babu/ Joy Chakraborty/Prosenjit Ganguly | SDT Architecture walkthrough by Joy/Rajesh | Completed
|  | 12:01 PM - 1:00 PM | Lunch
|  | 1:01 PM - 3:30 PM | SDT Understanding Continution | Rajesh Babu/ Joy Chakraborty/Prosenjit Ganguly |  | Completed
|  |  | Rally user stories & Code snippets |  | Discussed app 13 rally userstories Approach followed Rally Userstory -----> Acceptance Criteria -----> SDT screen Navigation -----> Code walkthrough ----> clarifications | Completed
|  |  | CLICK KT 1. Discussion regarding Master Data Management and dependencies. 2. Web Client and Mobile Templates for different Regions /roles. 3. User Management using IDM portal. 4. Discussion on the configurations for the new region roll-out. Click Configurations:- • Master data load to Click - Weekly • Web Client / Mobile Templates • Calendars • New region rollout related configurations |  | Prosenjit & Gopi had discussion | Completed
Loading of SDT calendar for the the public holidays in 2017 for all ASEAN countries, and pass the ID, MY, and TH
SDT Master files
|  |  | Pending topics from the Transition Tracker |  | Technical topics were covered | Completed
|  | 3:31 PM - 4:00 PM | Tea Break
|  | 4:01 PM - 5 : 30 PM | SDT Understanding Continution | Rajesh Babu/ Joy Chakraborty/Prosenjit Ganguly |  | Completed
|  |  | Rally user stories & Code snippets |  | Discussed app 13 rally userstories Approach followed Rally Userstory -----> Acceptance Criteria -----> SDT screen Navigation -----> Code walkthrough ----> clarifications | Completed
|  |  | CLICK KT 1. Discussion regarding Master Data Management and dependencies. 2. Web Client and Mobile Templates for different Regions /roles. 3. User Management using IDM portal. 4. Discussion on the configurations for the new region roll-out. Click Configurations:- • Master data load to Click - Weekly • Web Client / Mobile Templates • Calendars • New region rollout related configurations |  | Prosenjit & Gopi had discussion | Completed
|  |  | Pending topics from the Transition Tracker |  | Technical topics were covered | Completed
| 2017-01-05 | 10:00 AM - 12:00 PM | SDT Understanding i. Rally user stories & Code snippets ii. CLICK KT 1. Discussion regarding Master Data Management and dependencies. 2. Web Client and Mobile Templates for different Regions /roles. 3. User Management using IDM portal. 4. Discussion on the configurations for the new region roll-out. | Rajesh Babu/ Joy Chakraborty/Prosenjit Ganguly/ Anil |  | Completed
|  | 12:01 PM - 1:00 PM | Lunch
|  | 1:01 PM - 3:30 PM | Project Planning/ Project Monitoring/ Project End Activites | Rohit Handa/Chandramohan Gupta | Planned for 6th Jan morning session | Completed
|  | 2:01 PM - 3:30 PM | Middleware interaction with SDT | Sathyapa/ Kiran | Kiran has demonstrated | Completed
|  | 3:31 PM - 4:00 PM | Tea Break
|  | 4:01 PM - 5 : 30 PM | Database Handling | Haritha Gunturu/ Rahul | Rahul has demonstrated | Completed
| 2017-01-06 | 10:00 AM - 12:00 PM | Project Planning/ Project Monitoring/ Project End Activites Incident/Problem/Change Management GxP/ Non GxP Processes Configuration/ template changes during click deployments | Rohit Handa/Chandramohan Gupta |  | Completed
|  | 12:01 PM - 1:00 PM | Lunch
|  | 1:01 PM - 3:30 PM | Document Walkthrough | Rohit Handa/Chandramohan Gupta |  | Completed
|  | 3:31 PM - 4:00 PM | Tea Break
|  | 4:01 PM - 5 : 30 PM | Status updates on Transition Tracker & actions items with resoultions | Krishna Chaitanya |  | Completed

## Contact List
Contact Details
Name of the contact | SSO Id | Associated with Application / Area / Function | Customer / Vendor Name | Role | Email address | Work Location | Office Phone # | Cell Phone # | Availability Plan | Alternate contact during absence
Krishna Chaitanya Pabolu Venkata | 502690207 | SDT Application Transition | Capgemini | Transition Manager | Krishnachaitanya.paboluvenkata@ge.com | Bengaluru | 080-41007719 | 9900135167 | Offshore IST Hours | 9966857744
Waltz, Zachary | 212325680 | SDT Application | GE Healthcare | ITLP | zachary.waltz@ge.com | Waukesha | 0014147214136 |  | Onsite
Handa, Rohit | 212553016 | SDT Application | GE Healthcare | Sr Technical Project Manager | rohit.handa@ge.com | Bengaluru | 918040469514 | 9620171901 | Offshore IST Hours
Gupta, Chandramohan | 320000277 | SDT Application | GE Healthcare | Sr Technical Product Manager | Chandramohan.Gupta@ge.com | Bengaluru | 918040468265 | 9620206493 | Offshore IST Hours
Saha, Sanjoy K | 212042760 | SDT Application | GE Healthcare | Sr Manager - Program Management | sanjoy.saha@ge.com | Wauwatosa | 0012625443427 | 001262906313
Martand Thapliyal | 502675261 | SDT Application Support | TechM | Support Lead | martand.thapliyal@ge.com | Chandigarh | +91-172-666-8400 (Ext: 8380) | 9888802840 | 10:00 AM – 7:00 PM (IST) | 9873404075
Debashis Mohanty | 502671847 | SDT Application Support | TechM | Support Backup Lead | debashis.mohanty@ge.com | Bhubhneshwar | 8697730854 | 8697730854 | 10:00 AM – 7:00 PM (IST) | 9873404075
Joy Chakraborty | 502449179 | SDT Application Development | TechM | Architect | joy.chackraborty@ge.com | Noida | +91-120-617-6000 (Ext: 3151) | 9873404075 | 10:00 AM – 7:00 PM (IST) | 9966238811
Rajesh Babu Kallem | 502533753 | SDT Application Development | TechM | Dev Lead | rajeshbabu.kallem@ge.com | Hyderabad | +91-40-306-74119 | 9885051097 | 10:00 AM – 7:00 PM (IST) | 9966238811
Prosenjit Ganguly | 502536609 | Click Admin | TechM | Click Admin | prosenjit.ganguly@ge.com | Bhubhneshwar | 9831175596 | 9831175596 | 10:00 AM – 7:00 PM (IST) | 9873404075
Srini Divi | 502675262 | SDT Application Transition | TechM | Project Manager | Srinivas.divi@ge.com | Hyderabad | +91-40-306-74119 | 9966238811 | 10:00 AM – 7:00 PM (IST) | 9515223959
Saraswathi Nagaraj | 502693349 | SDT Project Manager | Capgemini | Project Manager | saraswathinagaraj@ge.com | Bengaluru | 080-41004070 | 9980159104 | Offshore IST Hours | 9980159104
Syed Farhan Husain | 502693352 | SDT Technical | Capgemini | Sr. Developer .NET | syedfarhan.husain@ge.com | Mumbai | 2297193 | 9920259651 | Offshore IST Hours | 9920259651
Suvarna Dmello | 502693358 | SDT Technical | Capgemini | Sr. Developer .NET | suvarna.dmello@ge.com | Mumbai | 2297193 | 9820402698 | Offshore IST Hours | 9820402698
Hita Soni | 502693353 | SDT Scrum Master | Capgemini | Sr. Developer .NET | hita.soni@ge.com | Mumbai | 2297191 | 7387460746 | Offshore IST Hours | 7387460746
Tejashree Bhagat | 502693354 | SDT Technical | Capgemini | Sr. Developer .NET | tejashree.bhagat@ge.com | Mumbai | 2297191 | 8976162303 | Offshore IST Hours | 8976162303
Jayesh Soni | 502693357 | SDT Technical | Capgemini | Developer .NET | jayesh.soni@ge.com | Mumbai | 2297191 | 7737657511 | Offshore IST Hours | 7737657511
Deepak Vishwakarma | 502693356 | SDT Technical | Capgemini | Developer .NET | deepak.vishwakarma@ge.com | Mumbai | 2297191 | 8652337229 | Offshore IST Hours | 8652337229
Monappa Prajna | 502693355 | SDT Technical | Capgemini | Sr. Developer .NET | prajna.monappa@ge.com | Bengaluru | 080-41005261 | 7353935716 | Offshore IST Hours | 7353935716
Sathyaraj Rajasekar | 502693350 | SDT Business Analyst | Capgemini | Business Analyst | sathyaraj.rajasekar@ge.com | Bengaluru | 080-41005261 | 7259777793 | Offshore IST Hours | 7259777793
Andrey Reiner | 502690034 | SDT Solution Architect | Capgemini | Consultant | andrey.reiner@ge.com | UK |  | 7904645273 | Offshore IST Hours | 7904645273

## Handover for CM
Status
Is the team member receiving KT going to perform the role of Configuration Manager for Project? |  | N | If Status is selected No (in cell D 2) then no need to fill this sheet and entire section can be left blank.
Sr. No. | Handover Items | Status* | Details received by New CM*
1. | Configuration Management Plan Read by New CM? | Not Applicable
2. | CM training done by New CM? | Not Applicable
3. | Project Stage at Handover: | Not Applicable
| Setup/Ongoing/ Project Delivery | Not Applicable
| SDLC Phase (for Dev Projects) | Not Applicable
4. | Does New CM know Configuration Status at present? | Not Applicable
5. | Is new CM aware of Itrack directory structure ? | Not Applicable
6. | Are Client supplied items are handed over to New CM? | Not Applicable
7. | Knowledge transfer for the areas – | Not Applicable
| Tools used for CM | Not Applicable
| Schedule for Baselining | Not Applicable
| Current Status of Configuration Items | Not Applicable
| Hardware/Environment Requirements for Baselining | Not Applicable
| Records for Reviews | Not Applicable
| Passwords Tools for Project documents if Any | Not Applicable
For Development Projects / Release based Maintenance Projects |  | Not Applicable
8. | Is Traceability Matrix Updated before handover? | Not Applicable
9. | Is New CM made aware of Baselining? | Not Applicable
| Next Baselining on : . | Not Applicable
10. | Baseline Audit records | Not Applicable
| Component Sign-Off | Name* | Date Signed* (mm/dd/yy)
Person Giving KT
Person Receiving KT

## Deliverables Handover
Sr. No | Deliverable Title / Tasks* | Deliverable Location* | Comments
Application Document links
1 | Business Solution Specs | Click ¦ Also shared a copy of BSS by Joy
2 | GxP documents location (MWS, BookId) | Chandra
3 | Click Client, Idm - all environments | Chandra
4 | Click RD-Web related accesses | Chandra
5 | GE Landscape Document | Chandra
6 | Oauth | https://ge.box.com/s/6780x57cng6yuavh0wlrlhnz9xmqywuq
7 | GxP documents location (MWS, BookId) | Chandra
8 | Non GxP documents (GE Box folder) | Chandra
9 | List of All CR's implemented by ClickSoftware for R1 release | http://supportcentral.ge.com/products/sup_products.asp?prod_id=368230
Application Environment links
1 | Siebel CRP | http://plt-crmintl.health.ge.com/emedical_enu
2 | Siebel iTEST | http://tst-crmintl.health.ge.com/emedical_enu/
3 | Siebel Prod | http://crmintl.health.ge.com/emedical_enu
4 | Click CRP/Sandbox | https://gehc-sb2-so.cloud.clicksoftware.com/clickschedulewebclient/default.aspx
5 | Click iTEST(Stage) | http://stg-sdt.gehealthcare.com/
6 | Click Prod | http://sdt.gehealthcare.com/
List of Areas on Ownership for Click Configurations
1 | Master data load to Click - Weekly | Prosenjit / Debashis
2 | Web Client / Mobile Templates | Prosenjit / Ankur
3 | Calendars | Prosenjit / Ankur
4 | New region rollout related configurations | Prosenjit / Ankur
5 | IDM Management | Prosenjit / Ankur
Use Cases/ Scenarios
1 | SDT Booking Create and Modify activity from Siebel | Refer Rally User Stories | Completed
2 | SDT Booking with appointment and without appointment | Refer Rally User Stories | Completed
3 | Bump job | Refer Rally User Stories | Completed
4 | Part Pickup Dependency Create and Modify | Refer Rally User Stories | Completed
5 | Site System Dependency Create and Modify | Refer Rally User Stories | Completed
6 | ES & LS Logic , FMI Due date and Desire date logic Walkthrough | Refer Rally User Stories | Completed
7 | Time Zone Conversion logic and API | Refer Rally User Stories | Completed
Completed
Application Access Needed
1 | SSO
2 | Configure GE mail
3 | Add GE email to the group notification
4 | Jabber login
5 | Webex login
6 | Clear Service Now exams
7 | Access to service now
8 | Access to application from Siebel
9 | IE enterprise mode
10 | Google chrome
11 | Click Webclient PRD
12 | Click Webclient and admin tool (staging) access
13 | Click logs access
14 | Click admin tool PRD access
User Access on Tools
1 | Rally | Chandra
2 | ServiceNow | Chandra
3 | SDT Mobile App | Click
4 | MWS | Middleware Team
5 | GE Box | Chandra
6 | Visual Planning Tool |  | Not Applicable
7 | MW Monitor tool
8 | Click access for raising Service cases. | Chandra
9 | Siebel | Chandra
10 | ALM | Chandra
11 | VPN Token | Chandra
| Component Sign-Off | Name* | Date Signed* (mm/dd/yy)
Person Giving KT
Person Receiving KT

## Action Plan
S.NO | Action Identified | Date Identified | Identified Through | Expected results | Stakeholders | Owner | Action Plan Team | Nearest milestone date | Completion date | Status As of | Comments
1 | Gathering GEHC_SDT Application_Technical Survey document | 2016-11-30 | Transition Process | To understand on the Application source code quality and application behaviour | All | Nagaraj, Saraswathi | TechM & Capgemini Teams | 2016-12-01 | 2016-12-01 | Completed | 30-Nov-2016: KC - Communicated to TechM team for updating the application details 1-Dec-2016: KC - Srini Divi shared the updated document
2 | Stage SSO id's have to be created for CG team to access SIEBEL browsers & Click Software | 2016-12-01 | KT Discussion | To access SIEBEL browser the team need to raise Stage sso id's | CG-SDT Team | Nagaraj, Saraswathi | CG SDT Team | 2016-12-02 | 2016-12-06 | Completed
3 | Application overview documents/links to be shared | 2016-12-01 | KT Discussion | Application understanding documents | All | Rajesh/Joy | TechM SDT Team | 2016-12-01 | 2016-12-02 | Completed
4 | Query log to be shared ahead of KT sessions | 2016-12-02 | KT Discussion | Share the Query log that has to be discussed in next day session ahead with TechM team | All | Nagaraj, Saraswathi | CG SDT Team | 2016-12-05 | 2016-12-05 | Completed
5 | Map the CG team SSO ids with SDT Group | 2016-12-05 | KT Discussion | For application support | CG-SDT Team | Nagaraj, Saraswathi | CG SDT Team | 2016-12-05 | 2016-12-05 | Completed
6 | Priortize on installing Visual studio for the developers | 2016-12-08 | KT Discussion | To have an application scenario specific discussion the tool & access is mandate | CG-SDT Team | Nagaraj, Saraswathi | CG SDT Team | 2016-12-10 | 2016-12-19 | Completed
7 | List of tools, softwares needed for Dev/Support team | 2016-12-08 | KT Discussion | To enable the list of softwares/tools needed for the new SDT team setup | CG-SDT Team | Rajesh | TechM SDT Team | 2016-12-08 | 2016-12-08 | Completed
8 | Need Sample status templates that are TechM is currently sharing with GE on project status | 2016-12-08 | KT Discussion | This would enable the new team continue on updating the status on project activities. | All | Srini Divi | TechM SDT Team | 2016-12-09 | 2016-12-12 | Completed
9 | Communicate on the update Transition plan with all Stakeholders | 2016-12-09 | KT Discussion | Share the updated transitions dates to all stakeholders | All | Krishna Chaitanya | Krishna Chaitanya | 2016-12-12 | 2016-12-12 | Completed
10 | Ops review process - Servicenow Graph generation for Incidents etc., | 2016-12-12 | KT Discussion | Understand on the ongoing Status updates to customer on the project deliverables | All | Srini Divi | TechM SDT Team | 2016-12-12 | 2016-12-16 | Completed | 15-Dec : Marthand will showcase on generationg the graphs from service now in the next session. Chandra to share the sample template
11 | Test cases for the SDT application | 2016-12-15 | KT Discussion | Test cases for the SDT application - To understand on the project tesing | All | Rajesh / Srini Divi | TechM SDT Team | 2016-12-16 | 2016-12-16 | Completed | 15-Dec : As per Srini confirmation the test cases are attached in rally tool for the corresponding user story Refer to Release 1.2
12 | Stage SSO id reference to replicate the similar access for the SIEBEL access | 2016-12-15 | KT Discussion | Stage SSO id reference to replicate the similar access for the SIEBEL access | All | Nagaraj, Saraswathi | CG SDT Team | 2016-12-16 | 2016-12-19 | Completed | 15-Dec : Contact Anil for the reference sso id to get SIEBEL access
13 | Revise KT tracker | 2016-12-16 | KT Discussion | Tracker GEHC_SDT_KT_Handover_Plan to be updated with revised dates for the topics to be covered by Chandra & Rohit | All | Krishna Chaitanya | Krishna Chaitanya | 2016-12-19 | 2016-12-21 | Completed
14 | Preparation of Roadmap for Face to Face workout session | 42720 | Status Meet | Preparation of Roadmap for Face to Face workout session | All | Saraswathi/Priya | CG SDT Team | 42729 |  | Completed
15 | Need inputs on Ongoing SDT Development activities for couple of regions from TechM | 2016-12-21 | KT Discussion | To understand on the ongoing TechM Dev activities like code baseline and release planning | All | Srini Divi/ Saraswathi/ Chandra | All | 2016-12-24 | 2016-12-23 | Completed
16 | Need to finalize on the timeslot for Middleware interaction with SDT with Satyapal /Kiran during F2F workout KTsession | 2016-12-28 | Status Meet | Need to finalize on the timeslot for Middleware interaction with SDT with Satyapal /Kiran during F2F workout KTsession | All | Krishna Chaitanya | Krishna Chaitanya | 2016-12-30 | 2016-12-29 | Completed | 28-Dec: Satyapal is on vacation till 30-Dec, upon his arrival will confirm on the dates
|  | Functional Know-how of the Application |  |  |  |  | 2016-12-01 |  | Anil will cover this topic in coming week 20-Dec: Anil covered the Siebel access
[7 empty] | 2016-12-01 |  | Anil will cover this topic in coming week 20-Dec: Anil covered the Siebel access

## Risk and Mitigation Plan
Risk and Mitigation Plan
Risk Identification |  |  | Risk Priortization |  |  |  | Risk Communication | Risk Mitigation | Risk Tracking |  |  |  | Revised Risk Priortization
Identification Date | Identified Risk | Possible Impact(s) | Probability of Occurrence | Detectability of Risk | Severity of Impact | RPN (Criticality) | Stakeholders Impacted and Communicated | Mitigation Initiative(s) | Status | Responsibility | Closure Date | Days Taken | Probability of Occurrence | Detectability of Risk | Severity of Impact | RPN (Criticality)
Program Related
2016-12-02 | TechM team highlights to cutdown 4hours KT sessions to 2Hrs for the reason the team is downsized and impacting their support activities 2. Per SOW the KT is supposed to be for 4 weeks, 1 week secondary support and 1 week primary support. | Delay in Transition | 1 | 2 | 2 | 4 | Entire Project/Team | Transition Manager to schedule a touch-point meeting to set down agreed points during the initial discussions 5-Dec-2016: Continue as usual with 2hrs Support KT in morning session & 2hrs Development KT in afternoon sessions The second risk need to be discussed with other stakeholders as well. 9-Dec-2016 Agreed to have agreed that these are the required resources for the KT. 11/30-12/23 – 4 weeks KT 12/26-12/30 – week of holiday 1/2-1/6 – 1 week secondary support 1/9-1/13 – 1 week primary support | Complete | Krishna Chaitanya
Total RPN (Criticality) (Category-wise) | [5 empty] | 4 | [9 empty] | 0
Process Related
2016-12-05 | TechM: It would be good to the TechM team if we have the query logs posted to us on daily basis to understand whether CG team is able to receive the contents correctly or not. We are not able to assess whether team is able to understand the things as intended or not as only very few queries were being asked during the sessions so far. | Incorrect measurement of Transition understanding | 3 | 3 | 2 | 18 | Entire Project/Team | Communicate and ensure to have an mail communication happens everyday from CG Team 5-Dec-2016 : Both teams agreed to have mail communication on the day to day understanding and share the question log ahead of next day session | Complete | Saraswathi Nagaraja | 2016-12-05 | 0 | 1 | 1 | 2 | 2
Total RPN (Criticality) (Category-wise) | [5 empty] | 18 | [9 empty] | 2
People Related
Total RPN (Criticality) (Category-wise) | [5 empty] | 0 | [9 empty] | 0
Knowledge Transfer Related
2016-12-02 | CG SDT Team : As we have very short time so it’s difficult to read each document in short span of time, and so we expect that if topics covered in deep with flow at backend explained in a good way would be great. | Application Understanding and supporting | 2 | 2 | 4 | 16 | Entire Project/Team | Transition Manager to schedule a touch-point meeting to set down agreed points during the initial discussions 5-Dec-2016: 1. Update the query log with the topics missed/need clarification. 2. Rajesh will cover the priority of access required for new team in 6-Dec-2016 KT sessions | Complete | Krishna Chaitanya | 2016-12-05 | 3 | 1 | 1 | 1 | 1
Total RPN (Criticality) (Category-wise) | [5 empty] | 16 | [9 empty] | 1
Technology Related
Total RPN (Criticality) (Category-wise) | [5 empty] | 0 | [9 empty] | 0
Contractual Related
Total RPN (Criticality) (Category-wise) | [5 empty] | 0 | [9 empty] | 0
Original Cummulative RPN (Criticality) of Project | [5 empty] | 38
Revised Cummulative RPN (Criticality) of Project | [5 empty] | 3
Note on B7: Available source of Risk Identification: Input and Process in SIPOC Proposal/ Contract Customer Communication Proposal Assumptions Estimation Assumptions Known Project Constraints Project Analysis Reports of Past Projects
Note on I7: Communicate Risks as below If color of RPN (Criticality) Box is : Red 1. Customer, as appropriate 2. Project Leadership Team 3. Appropriate Function Heads 4. Quality Manager/ Facilitator 5. Key Resources in Project Yellow 1. Project Leadership Team 2. Appropriate Function Heads 3. Quality Manager/ Facilitator 4. Entire Project Team Blue 1. Quality Manager/ Facilitator 2. Entire Project Team
Note on E8: 1 = Improbable 2 = Probable 3 = Very Likely
Note on F8: 3 = Difficult to Detect 2 = Moderately difficult to detect 1 = Easy to Detect
Note on G8: 8 = Catastrophic 4 = Critical 2 = Marginal 1 = Negligible
Note on H8: Risk Priortization Number (RPN) = Probability X Detectability X Severity
Note on O8: 1 = Improbable 2 = Probable 3 = Very Likely
Note on P8: 3 = Difficult to Detect 2 = Moderately difficult to detect 1 = Easy to Detect
Note on Q8: 8 = Catastrophic 4 = Critical 2 = Marginal 1 = Negligible
Note on R8: Risk Priortization Number (RPN) = Probability X Detectability X Severity

## Revision History
REVISION HISTORY OF WORK PRODUCT (to be maintained by projects)
# | Date | Version # | Section Changed | Details of changes made | Modified By
1 | 2016-11-16 | V1.0 | KT Plan | GEHC SDT Support Team Transition Plan | Krishna Chaitanya PV
2 | 2016-11-30 | V1.1 | All | Updated with team contacts & plan dates | Krishna Chaitanya PV
3 | 2016-12-12 | V1.1 | SDT KT Plan | Updated with 4 weeks KT plan dates + Secondary & Primary support dates | Krishna Chaitanya PV
4 | 2016-12-27 | V1.2 | F2F KT Agenda | Included new tab to cover F2F KT Agenda | Krishna Chaitanya PV
Not Started
In Progress
Completed
Not Applicable