## GE
Dispatch and Booking DevOps transition
Dates: | Jan 9th through the 12th
Location | Cap Gemini Office - Bangalore
Prerequisites: | Complete 75% ( ?) of Face to Face technical tranisiton from TechM to CG
Two Sessions:
1 | Technical and Process with: GE, TechM and Cap Gemini - Jan 4th, 5th and 6th
2 | GE Internal One Service strategy - Jan 9th to 12th
| Topic | Description | Outcome | Presenter | Duration | Date/Time
Agenda for Session 1 | Review Support Model | Review and walkthrough of the end to end process and all transition steps from ticket creation to resolution | Ensure all critical steps, tasks and handoff's in the process are covered. Action plan on any identified gaps. | CapGemini | TBD | TBD
| Review of current state and understanding of the App | Walkthrough of the Application, Business and process flow. | Ensure the support team has the background of the process and business functionality they will be supporting Action plan on any identified gaps. | CapGemini | TBD | TBD
| One Service Roadmap | Provide insight to the vendor team on the overall strategy of this application to the One Services strategy | Ensure vendor partners understand the big picture of the business process they are supporting | GE - TBD | TBD | TBD
| Dispatch Technical Architecture | Technical review of the applications, systems and processes used across the booking and dispatch cycle | Ensure vendor partners understand the full technical implementation and eco system of the application/s they are supporting. Action plan on any identified gaps. | CapGemini | TBD | TBD
| Transition Plan | Detailed review of the Transition plan and status Completed Tasks Resource Onboarding Technical Training Etc | Ensure all critical steps, tasks and handoff's in the process are covered. Action plan on any identified gaps. | TechM and Cap | TBD | TBD
| Communication Plan | Review of Op Mechs, Dashboards and communication plans the DevOps team will implement | Ensure we have the right level of communication, visibility and rigor Action plan on any identified gaps. | CapGemini | TBD | TBD
| Risks and WatchList | Based on experience - where are risks and help needed? - Click Support - Siebel Support | Highlight to leadership Action plan to close or monitor the gaps | CapGemini & GE (TBD) | TBD | TBD
| KT Wrap up | Technical deep dive on critical and complex transition topics | GE to ensure the key areas are being transitioned adequately | TechM and Cap | TBD | TBD
Agenda For Session 2
GE Internal | Leadership Update | Strategic technology eval Smax Predix options
| Key Gaps by Technology | Click Siebel
Key gaps by Region/ Functional
R's & R's
• ISDS (Chandra/Rohit roles) • CG KT • Mobile stability workout • Overall Funding • Architect way ahead (CG vs. GE FTE) • VPT • RACI

## Participants
GE | CG | TechM | Birlasoft
Rohit | Priya | Joy | Anil
Chandra | Saraswathi | Rajesh
Paul | Suvarna | Prosenjit
Sitara | Sathyaraj | Rahul
Sanjoy | Jayesh
Sean | Ebaad
Haritha
Krishna
Gaurav
Andrey
Gopi
Vivek Prabhu
Sajad
Vamsi
Ashish Deo
Time:9AM to 5PM
Dates | 4th Jan | 5th Jan | 6th Jan | 9th Jan | 10th Jan | 11th Jan | 12th Jan
GE | Rohit | Chandra/Rohit | Chandra/Rohit | All GE Folks | All GE Folks | All GE Folks | All GE Folks
CG | CG team | CG team | CG team | CG team | CG team | CG team | CG team
TechM | TechM Team | TechM Team | TechM Team except Rajesh | Joy & Rajesh | NA | NA | NA
Birlasoft | Anil | Anil | Anil | Anil | NA | NA | NA

## Day1-9Jan
Agenda | DevOps Model
Participants
GE Team - Rohit, Chandra, Sean, Paul, Sanjoy, Sitara
CG Team - Gaurav, Priya, Saraswathi, Sathyaraj, Suvarna, Jayesh, Ebaad, Krishna, Andrey, Gopi, Vamsi, Vivek, Ashish
Tech M team - Joy, Rajesh, Prosenjit
Birla Soft - Anil
Workout Session
`- | Time | Topics | Pitcher | Description | Outcome
Workout Session | 9:00 - 9:30 a.m | Meet and Greet | Capgemini
| 9:30 a.m - 10:30 a.m | Functional Understanding of SDT | Sathyaraj | Walkthrough of the Application, Business, process flow
| 10:30 a.m - 11:30 a.m | Capgemini Leadership meet | Capgemini
| 11:30a.m - 12:00 p.m | Dispatch Technical Architecture KT Wrap up | Andrey Capgemini/TechM | Technical review of the applications, systems and processes used across the booking and dispatch cycle Technical deep dive on critical and complex transition topics | Ensure vendor partners understand the full technical implementation and eco system of the application/s they are supporting. Action plan on any identified gaps.
| 12:00 p.m - 1:00 p.m | Lunch | Capgemini
| 1:00 p.m - 2:00 p.m | Review of DevOps Model:Session 1 | SathyaRaj | Support Model:Review and walkthrough of the end to end process and all transition steps from ticket creation to resolution | Ensure all critical steps, tasks and handoff's in the process are covered. Action plan on any identified gaps.
| 2:00 p.m -2:30 p.m 2:30 p.m - 3:30 p.m | Meet of Trace, SBOM and SIEBEL Team Review of DevOps Model:Session 2 | Capgemini/GE Suvarana | Devlopment Model:Review and walkthrough of the current development process and identify pain areas.Devise Agile / SCRUM implementation plan | Ensure the support team has the background of the process and business functionality they will be supporting Action plan on any identified gaps.
| 3:30 p.m - 4:00 p.m | Break / Tea
| 4:00 p.m - 5:00 p.m | Capgemini Capbility - ASE | Capgemini | A brief introduction to Accelerated Solutions Enviornment facility, brainstorm of pain areas and devising implementation / rollout plans
| 5:00 p.m - 5:15 p.m | Recap and Prelude

## Day2-10Jan
Agenda | Technical
Participants
GE Team - Rohit, Chandra, Sean, Paul, Sanjoy, Sitara
CG Team - Gaurav, Priya, Saraswathi, Sathyaraj, Suvarna, Jayesh, Ebaad, Krishna, Andrey, Gopi, Vamsi, Vivek, Ashish
Tech M team - None
Birla Soft - None
Workout Session
`- | Time | Topics | Pitcher | Description | Outcome
Workout Session | 9:00 a.m - 9:30 a.m | Meet and Greet | Capgemini
| 9:30 a.m - 10:30 a.m | Dispatch Quality attributes Improvement | Hita, Ebaad, Deepak, Tejashree | Review of current CAST results and plan to impove further | Roadmap for 2017 for improvement
| 10:30 a.m - 11:00 a.m | Transition Plan / communication Plan | Krishna | Detailed review of the Transition plan and status Completed Tasks Resource Onboarding Technical Training Etc Review of Op Mechs, Dashboards, esalation matrix and communication plans the DevOps team will implement like Email followup, Updating Stakeholders etc. | Ensure all critical steps, tasks and handoff's in the process are covered. Action plan on any identified gaps.
| 11:00 a.m - 12:00 p.m | Code Configuration/ Versioning Road ahead | Jayesh
| 12:00 p.m - 1:00 p.m | Lunch | Capgemini
| 1:00 p.m - 3:00 p.m | Devops Implementation | Jayesh | Review current state and define plan to devops implementation | Roadmap for Devops implementation for 2017, Phase wise
| 3:00 p.m - 4:00 p.m | Capgemini capability presentation - Predix | Capgemini |  | Ensure we have the right level of communication, visibility and rigor Action plan on any identified gaps.
| 4:00 p.m - 5:00 p.m | Devops Implementation- Continuation | Jayesh | Review current state and define plan to devops implementation
| 5:00 p.m - 5:15 p.m | Recap and Prelude

## Day3-11Jan
Agenda | GE Internal
Participants
GE Team - Rohit, Chandra, Sean, Paul, Sanjoy, Sitara
CG Team - Gaurav, Priya, Saraswathi, Sathyaraj, Suvarna, Jayesh, Ebaad, Krishna, Andrey, Gopi, Vamsi, Vivek, Ashish
Tech M team - None
Birla Soft - None
Workout Session
`- | Time | Topics | Pitcher | Description | Outcome
Workout Session | 9:00 a.m -9:30 a.m | Meet and Greet | Capgemini
| 9:30 a.m - 12:00 p.m | GE Internal:Leadership Update | GE Team | Strategic technology eval Smax Predix options
|  | Key Gaps by Technology | Chandra/Rohit | Click Siebel
|  | Key gaps by Region/ Functional & R's & R's | Chandra/Rohit
| 12:00 p.m - 1:00 p.m | Lunch | Capgemini
| 1:00 p.m - 2:00 p.m | • ISDS • Mobile stability • Overall Funding | Chandra/Rohit
Chandra/Rohit
| 3:30 p.m -4:00 p.m | Break / Tea
| 4:00 p.m - 5:00 p.m | • Architect way ahead (CG vs. GE FTE) • VPT • RACI & Escalation Matrix | Chandra/Rohit
| 5:00 p.m - 5:15 p.m | Recap and Prelude

## Day4-12Jan
Agenda | Mobility and BI
Participants
GE Team - Rohit, Chandra, Sean, Paul, Sanjoy, Sitara
CG Team - Gaurav, Priya, Saraswathi, Sathyaraj, Suvarna, Jayesh, Ebaad, Krishna, Andrey, Gopi, Vamsi, Vivek, Ashish
Tech M team - None
Birla Soft - None
Workout Session
`- | Time | Topics | Speakers | Remarks | Outcome
Workout Session | 9:00 a.m - 9:30 a.m | Meet and Greet
| 9:35 a.m - 10:35 a.m | BI team - Presentation
| 10:35a.m - 11:00 a.m | Break / Breakfast
| 11:00 a.m - 11:30 a.m | Capgemini Leadership meet | Capgemini
| 11:30a.m - 12:30 p.m | DCX team - Mobility
| 12:30 p.m - 1:30 p.m | Lunch
| 1:30 p.m - 2:00 p.m | Recap and Prelude