## Action Items
# | Action Items | Description | Owner | Priority | Status | Milestone(30-60-90) | Comments
1 | Mobile app issue | Click Mobile App has sync issues which will be fixed in patch 9 deployed by the Click Team. | Gopi/Andrey | High | In-Progress | 30 days | Prep sessions. More on investigation. CSC should be able to view the last sync in CS
2 | Performance of SDT | Performance of SDT depends on the following factors: SDT booking opening from Siebel takes some time to get loaded on the Booking Application UI. Click Web services take approx 23 seconds to respond back to SDT. SDT performance can be improved by working on the low risks items identified by CAST analysis. New technical User story will be written in Rally | Hita/Suvarna | High | Open | 90 days
3 | Mobility team or Tiger team to be formed | To resolve click mobile issues, Tiger team members to be identified. RCA and CA to be taken | Saraswathi/Rohit | High | Open | 30 days
4 | Checkmysite-Sitara to provide the demo | Overview of CMS will be provided by Sitara to CG team | Sitara | Low | Completed | 30 days | CMS demo given to the CG team by Hansraj Singh
5 | Bump load is done manually which needs to be improved | Discuss on the functionality with the Product Owners | Sathyaraj | Medium | Open | 60 days
6 | SDT team member to understand Master data files | Connect with Haritha and understand the master files. Get KT | Prajna/Tejashree | Medium | In-Progress | 30 days
7 | Google API incidents | Learn about Google places and try to implement it in code | Hita/Ebaad | High | Completed | 30 days | Delivered the changes in release 1.3
8 | Sentry to be moved to check with Venkat(GE Corporate) | Physical layers to be revisited. Confirm with Venkat. Information should be shared across. | Saraswathi/Jayesh | High | In-Progress | 30 days | 11/01/2017: Connected with GE Corporate
9 | Interfacing Rally with Jira/ServiceNow | CG to work on the interfacing and auto emailing function | Saraswati/Ebaad | Medium | In-Progress | 30 days | Ebaad to connect with Gaurav
10 | Fiddler - Code review and server instance | CG to work on the code review part on Fiddler | Farhan/Ebaad | High | Open | 30 days
11 | Logger-Some R&D required
12 | Improvements in Error message to users, friendly message | Customized error messages to be displayed | Hita/Tejashree | Medium | Open | 60 days
13 | SBOM -Demo to Sitara | SBOM demo | Saraswathi/Namratha | Low | In-Progress | 30 days | Meeting to be scheduled from Namrata(SBOM team)
14 | To discuss on esclation mechanism | Saraswathi to incorporate the escalation matirx in the communication model | Saraswathi/Sathyaraj | High | In-Progress | 30 days
15 | Problem manager to priotize the problem management issues | GEHC to find a problem manager from GE corporate | Chandra/Rohit | Medium | Open
16 | Weekly review on status of the incidents | CG to setup a weekly meeting | Sathyaraj | High | In-Progress | 30 days
17 | A common link to get the service now tickets in all. | Dashboard/Reporting | Sathyaraj/Ebaad | High | In-Progress | 30 days
18 | CLICK focus areas | Pain areas to be discussed and further actions can be taken based on the same | Gopi/Andrey | High | In-Progress | 60 days
19 | Identifying Problem Manager from GEHHC team | Rohit to find a Problem Manager from the corporate team | Rohit | Medium | Open
21 | Development Chart | Prepare a Development chart | Suvarna/Hita | High | In-Progress | 30 days
22 | Environment setup | Environement details and release related details | Jayesh | High | In-Progress | 30 days
23 | Release path and bug fix path | Flow should be captured by CG | Jayesh | High | In-Progress | 30 days
24 | Non functional requirements to identify | GEHC to share non functional requirements | Chandra/Rohit | Medium | Open | 30 days
25 | Sonar queue, Coverity | Connect with testing team | Tejashree/Saraswathi | Medium | Open | 60 days
26 | Click devops mapping | Incorporate SDT with Click. Connect with Ravi/Amitabh | Suvarna | Medium | In-Progress | 30 days
27 | IDM access | CG Click team to connect with Paul to get access and work closely with FSEs/Super User | Gopi | High | Open | 30 days
28 | GE Box - SOPs of incidents & missed out items | SOPs to be prepared for CLICK , SDT and Support Process. | Gopi/Ebaad/Sathyaraj | Medium | Open | 60 days
29 | Confluence | Rohit and Chandra to provide access | Rohit | Low | Open | 60 days
30 | On support calls - L1 support from GEHC | Chandra to check and confirm on L1 support - on call support | Chandra/Rohit | Medium | Open | 30 days
31 | P1/P2 establish SLAs define/refine | Define SLA buckets wrt to PO, Super User | Saraswathi | High | Open | 30 days
32 | Mobile/Laptop | ITIM support on Mobile/Laptop | Saraswathi | High | Open | 30 days
33 | Agile Op Mechh | Operation Mechanism on Agile | Suvarna | Medium | In-Progress | 60 days
34 | Daily standup | Scrum Master to schedule daily scrum calls | Suvarna | Low | Open | 30 days
35 | Communication Plan(update ppt - team, roles, incorporate agile communication methods) | Update the Communication model and escalation matrix | Sathyaraj/Saraswathi | High | Open | 30 days
36 | VPT - POC | POC to be created inline with VPT | Saraswathi/Sathyaraj | Low | Open | 90 days
37 | VPT/Spotfire - access details | Provide SSO to Paul | Saraswathi/Sathyaraj | Low | Open | 30 days
38 | GE AVS scan report | Rohit to provide inputs | Rohit | Low | Open | 60 days
39 | Regression testing | CG to perform regression testing | CG team | Medium | On-Hold | 90 days | Performed during code changes
40 | Planning poker - estimation | Scrum Master to provide a demo | Suvarna | Medium | Open | 60 days
41 | VPN token | GEHC to provide VPN token | Paul/Rohit | Medium | Open | 30 days
42 | Data from Click wrt VPT | connect with Click | Gopi | Low | Open | 90 days
43 | Modified/Changed code files from TechM for Release 1.3 | Send a mail to Rohit to followup | Rohit/saraswathi | High | Open | 30days
44 | Rally Demo | Demo on Rally by Rohit | Rohit | Medium | Open | 30days
45 | CAST report analysis by Andrey on Code improvement areas | Setup a call with Andrey & Rohit | Andrey/Rohit | High | Open | 30days

## MOM
# | Action Items | Description | Comments
1 | Functional Understanding from CG
2 | Session on TRACE from Chandra | TRACE session completed on Day2 workout | Chandra

## Standard Processes
Standard process to be followed
1 | Gaps and action items to followup
2 | To use Service Now for siebel issues
3 | To add userstory to Rally based on sequence
4 | RCA related defects / incidents are analyzed
5 | Communication plan on incident update which covers both good and bad
6 | Insisting Users to join the incident call
7 | Problem should be logged in Rally
8 | User story for perfomance improvement n code improvements

## Sheet2
High | 30 days | Completed
Medium | 60 days | In-Progress
Low | 90 days | On-Hold
Open

## Sheet5
3 | Siebel data-how to get the data and SLA calculation.
4 | How to determine late start and early start

## Sheet1
System | Comments
Mobile | Investigation is needed. Plan for investigation. Prep sessions
Involve GE teams in prep sessions. Identify the GE team
Reports on Good/Bad clicks - FSE mobile Usage
Click & Ge log files
SSO/Connectivity - Connection details
Infra on mobile

## Internal Action Items
S.NO | Action Identified | Date Identified | Expected results | Owner | Completion date | Status | Comments
1 | Stage SSO id's have to be created for CG team to access SIEBEL browsers & Click Software | 2016-12-01 | To access SIEBEL browser the team need to raise Stage sso id's | Nagaraj, Saraswathi | 2016-12-06 | Completed | Siebel CRP & Itest -still pending for Ebaad. Deepak Is facing issue with
2 | Application overview documents/links to be shared | 2016-12-01 | Application understanding documents | Rajesh/Joy | 2016-12-02 | Completed
3 | Query log to be shared ahead of KT sessions | 2016-12-02 | Share the Query log that has to be discussed in next day session ahead with TechM team | Nagaraj, Saraswathi | 2016-12-05 | Completed
4 | Map the CG team SSO ids with SDT Group | 2016-12-05 | For application support | Nagaraj, Saraswathi | 2016-12-05 | Completed
5 | Priortize on installing Visual studio for the developers | 2016-12-08 | To have an application scenario specific discussion the tool & access is mandate | Nagaraj, Saraswathi | 2016-12-19 | Completed | Still pending with
6 | List of tools, softwares needed for Dev/Support team | 2016-12-08 | To enable the list of softwares/tools needed for the new SDT team setup | Rajesh | 2016-12-08 | Completed
7 | Need Sample status templates that are TechM is currently sharing with GE on project status | 2016-12-08 | This would enable the new team continue on updating the status on project activities. | Srini Divi | 2016-12-12 | Completed
8 | Communicate on the update Transition plan with all Stakeholders | 2016-12-09 | Share the updated transitions dates to all stakeholders | Krishna Chaitanya | 2016-12-12 | Completed
9 | Ops review process - Servicenow Graph generation for Incidents etc., | 2016-12-12 | Understand on the ongoing Status updates to customer on the project deliverables | Srini Divi | 2016-12-16 | Completed
10 | Test cases for the SDT application | 2016-12-15 | Test cases for the SDT application - To understand on the project tesing | Rajesh / Srini Divi | 2016-12-16 | Completed
11 | Stage SSO id reference to replicate the similar access for the SIEBEL access | 2016-12-15 | Stage SSO id reference to replicate the similar access for the SIEBEL access | Nagaraj, Saraswathi |  | In Progreaa | Anil to provide the responsibilties
12 | Andrey to take up the SDT arcitecture | 2016-12-20 | Andrey to present the understanding of SDT architecture. | Andrey |  | Yet to intiate
13 | Cast Demo to move in Workout session | 2016-12-20 | Cast Demo to happen in Jna'17 with all GE and CG folks | Saraswathi/Hita |  | Yet to intiate
14 | GIT hub code versionning control | 2016-12-20 | Git hub intergartion with VS 2013 to finish by month end | Saraswathi/Jayesh |  | In progress
15 | Code files from TechM | 2016-12-20 | To get the changed files alone from techM to intergarate in the production code | Saraswathi/Jayesh |  | In progress
16 | Commnicaion plan | 2016-12-20 | Email folloups and Update to stakeholders even during success stories | Saraswathi |  | In progress
17 | Visual Planning Tool | 2016-12-20 | Need to understand on the VPT and any access required | Saraswathi |  | In progress
18 | Sschedule for support team frm Jan'17 | 2016-12-21 | Since from Jan'17 we are secondary do we need to work in shifts | Saraswathi |  | In progress
19
20