## Slide 1: GEHC SDT Weekly Status Report
02/02/17

## Slide 2: Open Actions
Action item | Owner | Forum | Expected Closure Date | Owner Comment | Status
CLICK certification to four of our SDT Team members | CG Team | Weekly Status | 05-Feb-2017 |  | In Progress
Mobility Team or tiger team to be formed to resolve all CLICK mobile issues | Rohit | Jan’ 17 Workout | TBD |  | In Progress
Performance issues: SDT Booking and Architecture Assessment. | Hita/Andrey | Jan’ 17 Workout | TBD |  | In Progress
Ownership on Tickets/Process adherence(Agile Mechanism) | Suvarna/Sathyaraj | Jan’ 17 Workout | Ongoing |  | In Progress
Release management(Deployment activities for Release 1.3) | Jayesh/Tejashree | Jan’ 17 Workout | 03-Feb-2017 |  | In Progress
GEHC to find a problem manager from GE corporate | Chandra | Jan’ 17 Workout | TBD | Will identify the problem manager when we have problem in hand. | On Hold
GEHC to share nonfunctional requirements | Chandra | Jan’ 17 Workout | TBD | Few are identified from Rally | In Progress
GEHC to check and confirm on L1 support - on call support | Chandra | Jan’ 17 Workout | TBD | we need laptops and VPN for team members to start | In Progress
Analysis and fixing of defects raised by Testing team and Business users. | CG Dev | Defect triage | TBD |  | In Progress

## Slide 3
Health of the Engagement
Highlights
Help Needed
VPN token for Gopi M and Farhan
Click DB access(Prod, Stage, Sandbox) for Gopi
Weekly Snapshot – 02/02/17
11 Open Defects from UAT and 2 defect from Testing team may lead to quality issues.
Risk / Issues / Challenges
Successful CLICK Master data load in Production, Sandbox and Stage environments.
R1.3 Release changes - Roll out 4 (Philippines, Singapore, Vietnam and Indonesia) regions in sandbox and stage.
CLICK R2.1.0 Deployment on SB1.
Vietnam Non availability(NA) issue, Messages view removal.
Deployment of R1.3 in staging is completed and UAT in progress.
Open defects (DE137, DE139 and DE140) tracked to closure.
GREEN

## Slide 4: Focus Area Updates
Focus Areas | Owner | Status | Comments
Mobile Sync Issues | CG Team | In Progress | Analysis in progress on already 13 existing CLICK support cases.- 5 issues are fixed and fixes will be part of R2.1.0, or Patch 9 /10 . Consolidated all CLICK Mobile Sync issues discussion in progress with Tiger team, Mobile iron and SSO team.
SDT Booking Performance Issues | CG Team | In Progress | Identified some of the properties values set w.r.t. click which are fixed, we need to move those to Constant file. Analyzed the code for optimization (Error messages which needs to be centralized and can be moved to Constant file or .Resource file)
Release Management | CG Team | In Progress | Release 1.2, 1.3 branch created in GIT HUB Release 1.3 Publish code repository created in GIT HUB Release check list preparation in progress
Incident Management | CG Team | Ongoing | Streamlining incidents w.r.t CLICK support cases Problem ticket creation process finalized.
Support and Development Process streamlining | CG Team | Ongoing | Daily SCRUM calls initiated and actions tracked to closure Ensuring all email communication to have incident ticket created. Internal defect tracker is maintained to track the QA/UAT defects and owners defined for each defect.
Initial assessment on SDT Booking tool | CG Team | In Progress | Andrey has designed a high level architecture for SDT booking.

## Slide 5: Incident Update
Awaiting third party –category is with CLICK
15 SDT Schedule / Mobile Issues
  13 - CLICK Mobile issues
  1 - Known error/issue
  1 - Master Data
Inferences
Chart: Problem tickets
| Known Error / Pending CA | Open
Total | 1 | 2
Chart: Incident Tickets
| Awaiting 3rd Party | Awaiting User Info | Resolved | Resolved – Awaiting Problem | Closed | Grand Total
Count of Number Total | 15 | 1 | 1 | 2 | 6 | 25

## Slide 6: Incident Tickets
Incident Management |  |  |  | 
Incident # | Module | Key Words | Status | Problem #
INC1370193 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1418668 | SDT Schedule | Master Data | Awaiting 3rd Party | NA
INC1420698 | SDT Schedule | Scheduled - Known Error | Awaiting 3rd Party | NA
INC1435230 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1435245 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1435289 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1435961 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447060 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447037 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447031 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1446914 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447042 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1447028 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1454094 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1463913 | SDT Mobile | Mobile sync Issue | Awaiting 3rd Party | NA
INC1464027 | SDT Booking | Click Issue | Awaiting User Info | NA
INC1285226 | SDT Booking | Email Activity | Resolved – Awaiting Problem | PRB0045556
INC1310582 | SDT Booking | Performance - Connectivity | Resolved – Awaiting Problem | PRB0045895
INC1448985 | SDT Mobile | Access | Resolved | NA
Problem Management |  |  |  | 
Problem # | Module | Keyword | Status | 
PRB0045855 | SDT Booking | Google API | Open | 
PRB0045895 | SDT Booking | Email Activity | Open | 
PRB0045475 | SDT Booking | Performance - Connectivity | Known Error / Pending CA | 

## Slide 7: The Team
Project Management | Program Manager | Priya Patra
 | Solution Architect | Andrey Reiner
 | Project Manager | Saraswathi Nagaraj
 | Business Analyst/Incident Manager | Sathyaraj Rajasekar
 | Scrum Master | Suvarna Dmello
CLICK | CLICK SME | Gopi M
 | CLICK SME | Preeti Sagar
DevOps Team | Technical Lead | Hita Soni
 | SDT Architecture | Farhan Husain Syed
 | Configuration Manager | Tejashree Bhagat
 | Release manager | Jayesh Soni
 | Senior .NET Developer | Prajna Monappa
 | .NET Developer /Testing Spoc | Ebaad Chowdhry
 | .NET Developer | Deepak Vishwakarma

## Slide 8: THANK YOU