## Slide 1: GEHC SDT Weekly Status Report
03/30/17

## Slide 2: Open Actions
Action item | Owner | Forum | Expected Closure Date | Actual Closure Date | Owner Comment | Status
Mobility Team or tiger team to be formed to resolve all CLICK mobile issues. | Rohit/Gopi | Jan’ 17 Workout | TBD |  | Monitoring the debug logs which are activated for 20 FE’s in production. | In Progress
Performance issues: SDT Booking and Architecture Assessment. | Hita/Andrey/Urmila/Chandra | Jan’ 17 Workout | 28-Feb-2017 |  | Andrey came up with one more new analysis. Implemented 2 ideas in CRP | In Progress
Ownership on Tickets/Process adherence(Agile Mechanism) | Suvarna/Sathyaraj | Jan’ 17 Workout | Ongoing |  |  | In Progress
GEHC to check and confirm on L1 support - on call support | Chandra/CG | Jan’ 17 Workout | TBD |  | No services available in ServiceNow tool. Need to look for a workaround. | In Progress
CLICK DB access for CG team GE to setup a separate call to discuss | Chandra | WSR meeting | TBD |  | Trying to leverage Trace DB (Hansraj & team) for backup DB setup | In Progress

## Slide 3
Health of the Engagement
Highlights
Help Needed
Need resolution to infrastructure related queries and common forum to resolve - Chandra
Need support on performance related issues on CLICK side – Urmila
Weekly Snapshot – 03/30/17
Without the CLICK environment(Server) details its difficult to understand the data flow from CLICK mobile to CLICK SO(Service Optimization) servers - Rohit/Chandra
Risk / Issues / Challenges
GREEN
  SDT Dev Instance Realignment-SB1 and SB3 e2e Testing Completed
  Weekly Master data uploaded successfully
  Code Implementation is completed for User Stories US145 and US134. testing in progress
  Performance Optimization: SB3 - Index created in Structure tool

## Slide 4: Focus Area Updates
Focus Areas | Owner | Status | Comments
Mobile Sync Issues | CG Team | In Progress | Yet to receive end to end environments details from CLICK team which was requested but they denied due to policy reasons. CG mobile team to share the document on background mode activation. Debug log activated for all 20 FE’s and Monitoring FE’s debug log.
SDT Booking Performance Issues | CG Team | In Progress | US181,US183- Code analysis done for PartPickDependency, GetTasksResponseOrBumpCheck methods US156-Indexing mechanism-Index created in Structure tool US145-FMI Logic code changes implementation in SDT US134-Code implementation and testing for reducing timezone conversion calls US175-Consolidating the list of error messages in SDT and confirming with business regarding the new messages US174-Analysis done To filter the tasks obtained in the method GetTasksRequestByPropertyName
Release Management | CG Team | Ongoing | Release check list was created and it is updated in our Release readiness check call.
Incident Management | CG Team | Ongoing | Streamlining incidents w.r.t CLICK support cases Problem ticket creation process finalized. Incidents reported in this week are closed.
Support and Development Process streamlining | CG Team | Ongoing | Agile metrics identified and tracked through Rally. Ensuring all email communication to have incident ticket created. Internal defect tracker is maintained to track the QA/UAT defects and owners defined for each defect.

## Slide 5: Agile Metrics - Development
Inferences
SDT Iteration 3 – 21st Mar to 31st Mar ‘17
Iteration Burndown Chart:
During Sprint planning added technical user stories in the sprint accepted by product owner.
Prioritized users stories by Product owner based on the performance analysis.
Iteration Cumulative Flow Diagram
First day of the Sprint . 5 user stories added in the sprint backlog.
2-3 user stories added on day 2 after performance assessment discussion.
Team started working on 5 user stories which shows the tasks are in progress.
2 user stories are done with the development and deployed in CRP for the testing team to test.
Inferences

## Slide 6: Agile Metrics - Support
SDT Click, Support and Incidents
Iteration Support Burndown Chart:
Support activities keep on added up on a daily basis based on the support tickets that we receive. Hence there’s a mismatch with ideal.
End of the sprint, all tickets are closed and all the user stories are accepted by Product owner.
Iteration Cumulative Flow Diagram
The tasks related to Release 2.1 and 2.2 and 6 incidents are completed
5 incident tickets are in-progress out of which some of them are waiting for third part or user info.
3 tickets are in defined state.
Inferences
Support Iteration 4 – 16th Mar to 31st Mar ‘17

## Slide 7: Agile Metrics – Velocity Chart
SDT
Velocity Chart
SDT Iteration 1
  Velocity of team:50 story points
  Accepted By PO: 13 story Points
  US85 and US 97 –Accepted by PO as these user stories are already deployed in production as part of release 1.3.1
  Iteration length: 10 days(2 weeks)
SDT Iteration 2
  Velocity of team: 9 story points
  Accepted By PO: 9 story Points
  Iteration length: 5 days(1 week)
Inferences
Chart: 
| SDT Iteration 1(02/14/2017 - 02/27/2017) | SDT Iteration 2(03/06/2017 - 03/10/2017)
Velocity(Story Points) | 50 | 9
Accepted By PO(SPs) | 13 | 9

## Slide 8: Agile Metrics – Velocity Chart
Support
Velocity Chart
Support Iteration 1
  Velocity of team:5 story points
  Accepted By PO: 5 story Points
  Iteration length: 8 days
Support Iteration 2
  Velocity of team:20 story points
  Accepted By PO: 19 story Points
  Iteration length: 12 days
Support Iteration 3
  Velocity of team:20 story points
  Accepted By PO: 20 story Points
  Iteration length: 11 days
Inferences
Chart: 
| Support Iteration 1(02/01/2017 - 02/10/2017) | Support Iteration 2( 2/13/2017 - 2/28/2017) | Support Iteration 3(03/01/2017 - 03/15/2017)
Velocity(Story Points) | 5 | 20 | 20
Accepted By PO(SPs) | 5 | 19 | 20

## Slide 9: Agile Metrics – Resource Utilization
Weekly resource Utilization(27th Mar 2017 – 31 Mar 2017)
Chart: 
| Hita Soni | Farhan Hussain | Tejashree Bhagat | Jayesh Soni | Ebaad Chowdhry | Deepak Vishwakarma | Prajna Monappa | Sathyaraj Rajasekar | Gopi Mottai | PreetiSagar Godi | Suvarna Dmello | Urmila Gumata | Binu Mohan | Ramesh, Dhivyabharathi
Total Available Hrs per Sprint | 32 | 24 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 24 | 24 | 32 | 32
Hours Spent on Sprint Ceromonies | 5.8 | 4.35 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 4.35 | 6 | 4.35 | 5.8 | 5.8
Ge meetings/Emails | 12 | 9 | 4 | 4 | 4 | 4 | 4 | 12 | 16 | 7.5 | 9 | 9 | 4 | 4
Support | 5 | 6 | 2 | 10 | 8 | 9 | 12 | 3
Total Available Hours | 14.2 | 10.65 | 17.2 | 16.2 | 20.2 | 12.2 | 22.2 | 6.2 | 1.2 | 0.15 | 6 | 10.65 | 22.2 | 22.2
Hours Scheduled (spent on tasks) | 12 | 8 | 14 | 13 | 19 | 9 | 21 | 3 | 0 | 4 | 10 | 19 | 19
Resource Utilization (in %) | 93.125 | 88.9583 | 90 | 90 | 96.25 | 90 | 96.25 | 90 | 96.25 | 99.375 | 91.6667 | 97.2917 | 90 | 90

## Slide 10: Incidents Update
9 incident tickets are resolved/closed
10 Awaiting 3rd party
8 Awaiting User Info
Inferences

## Slide 11: Incident Tickets
Incident Management |  |  |  | 
Incident # | Module | Key Words | Status | Queue wait time
INC1464027 | SDT Booking | Click Issue | Awaiting User Info | a month ago
INC1477114 | SDT Booking | Mobile Sync Issue | Awaiting User Info | 2 months ago
INC1480772 | SDT Mobile | Mobile sync Issue | Awaiting User Info | 2 months ago
INC1735928 | SDT Schedule | Click Issue | Awaiting 3rd Party | 29 days ago
INC1736222 | SDT Schedule | Click Issue | Awaiting 3rd Party | 28 days ago
INC1738700 | SDT Module | Click Issue | Awaiting 3rd Party | 28 days ago
INC1747182 | SDT Mobile | Click Issue | Awaiting 3rd Party | 23 days ago
INC1754593 | SDT Module | Click Issue | Awaiting 3rd Party | 21 days ago
INC1766606 | SDT Module | Mobile Sync Issue | Awaiting 3rd Party | 15 days ago
INC1777886 | SDT Module | Click Issue | Awaiting 3rd Party | 10 days ago
INC1778499 | SDT Module | Click Issue | Awaiting 3rd Party | 10 days ago
INC1779626 | SDT Module | Click Issue | Awaiting 3rd Party | 9 days ago
INC1781463 | SDT Module | SDT Booking issue | Awaiting User Info | 9 days ago
INC1782655 | Click | Click Issue | Awaiting User Info | 8 days ago
INC1787373 | Click | Click Issue | Awaiting User Info | 7 days ago
INC1787399 | Click | Click Issue | Awaiting User Info | 7 days ago
INC1787868 | SDT Module | SDT Booking issue | Awaiting User Info | 6 days ago
INC1793968 | Click | Click Issue | Awaiting 3rd Party | 4 days ago
Problem Management |  |  |  | 
Problem # | Module | Keyword | Status | Incident #
PRB0045855 | SDT Booking | Google API | Open | INC1371682, INC1389372, INC1357120
PRB0045895 | SDT Booking | Email Activity | Open | INC1285226
PRB0045475 | SDT Booking | Performance - Connectivity | Known Error / Pending CA | INC1310582

## Slide 12: THANK YOU