## SDLC Process
|  | Items | Owner | Work Product | Development | Support - CRs | Comments
Sprint |  | Requirement Gathering | Business | Rally Update | Y
|  | User Story documentation | Velu /Namrata | Rally Update | Y
|  | Adding high level acceptance criteria | Velu /Namrata | Rally Update | Y
| M | Sign off from Product Owner on acceptance criteria | Velu / Namrata |  | Y |  | To be updated in Notes section
|  | Impact Analysis | Project Team | Rally Update | Y
|  | Unit test case creation | Bharath | Test cases | Y |  | To be atatched to User Story
|  | Review - self | Project Team |  | Y
|  | Review - Peer | Project Team | Defects logged against User Story | Y
|  | Review - TL | Velu / Namrata | Defects logged against User Story | Y
|  | Integration Test case creation | Bharath | Test cases | Y |  | To be uploaded in Rally
|  | Review - self | Project Team | Defects logged against User Story | Y
|  | Review - Peer | Project Team | Defects logged against User Story | Y
|  | Review - TL | Velu / Namrata | Defects logged against User Story | Y
|  | Construction | Project Team | Code Comitted in GIT | Y
|  | Junit Test case creation | Project Team | Junit Test cases | Y |  | 10% Quality probe
|  | Unit Testing | Project Team | Defects logged against User Story | Y
|  | UnitTest Result creation | Project Team | Junit Test case Results | Y |  | Console log to be uploaded in the User Story
| M | Unit Test result review and Sign off | Project Team / Business |  | Y |  | To be updated in Notes section
|  | Code Review - Self | Project Team |  | Y
|  | Code Review - Peer | Project Team | Defects logged against User Story | Y
|  | Code Review - TL | Velu | Defects logged against User Story | Y
| M | Sign off by Architect | Architect / Gopal | Defects logged against User Story | Y
|  | Internal Dev testing | Project Team | Defects logged against User Story | Y
|  | Internal Dev defect Resolution | Project Team |  | Y
|  | Code Scan - CAST | Project Team | CAST Result | Y |  | CAST Result to be uploaded per Sprint in Rally Maintain / Improve TQI
| M | Sign off by Architect | Architect / Gopal | Sign off in Rally | Y
|  | Internal QA testing | Bharath | Defects logged against User Story | Y
|  | Internal QA defect Resolution | Project Team | Rally update | Y
|  | Project Integration Testing | Project Team | Rally update | Y
|  | Project Integration test result creation | Project Team | Rally update | Y |  | Results to be attached to user story
| M | UAT Sign off | Business/ Velu | Rally Update | Y |  | Story to be marked as A
|  | Staging testing | PST/ Project Team | Rally Update | Y |  | Note section to be updated
|  | Staging Defect Resolution | Project Team | Rally Update | Y |  | Note section to be updated
| M | Milestone

## Rally Updates
User Story Format
As a <type of user>, I want <some goal> so that <some reason>.
Acceptance Criteria Format
Bulleted points on what is required for business or porduct onwer to accept the story
Notes section
To be updated daily by SCRUM Master based on daily standup call with updates
Task Structure Format
Each User story should have the following sub - tasks
1. Construction
2. Review
3. Unit Testing
4. System Testing
5. Architect review
Sprint Closure
All User stories to be accepted to close Sprint
SCRUM Master to update Notes section on every standup meeting call
Project Team to update the tasks before the standup call
User Story to be marked as C post attaching test cases, test results and closure of defects
User Story to be marked as A post UAT acceptance sign off
To conduct Retrospection after each Sprint - MOM of the retrspection meeting to be circulated
To check for improvements Sprint on Sprint ( To be decided)

## Release Process
Project Phase | Deliverables | Remark | Location
Release Documents | Gxp Assesment | Gxp Assesment is the key document for Application Deployment | My WorkShop
| SDS, SRS & URS | Supporting Documents for the Application | My Workshop
| Test case and Test Reports | Evidence for Application functionalities | My Workshop | URS - User Requirment Specification
| Traceability Matrix | Capturing Requirements against Test Cases | My Workshop | SRS - System Requirement Specification
SDS - System Design Specification
Change Control | Review & Approval of Release Docs | Change Control in Service Now for Service Delivery Approval | Attach in CC | Test Plan and Test Results ( Unit and Integration Testing)
| Release Document | Comprehensive document for the changes and steps | Attach in CC | Traceability Matrix
| Implementation or Deployment Doc | For Run team which includes DBA, Cloud Team | Attach in CC