## User Stories
SDT Booking User story Board
User Story# | User Story Name | Description | Acceptance Criteria | Definition of Done | Owner | Start Date | Iteration | Expedite | Notes
US#84 | Performance Tuning | 1. In the code there are unreferenced data members, which unnecessarily hold memory spaces in the class object. 2. In the code there are instances wherein objects are instantiated in loops, because of this action there is increase in memory usage which leads to memory leakage causing longer process timings for that particular function. 3. There are many instances of redundant code, duplicate code snippets in Functional methods can be clubbed in single method to avoid code redundancy. | To check and verify that all the following criteria is met:- 1. Code improvements: a. Remove all the unused data members (we have got the list from cast) b. Remove commented code and add relevant commenting for ensuring proper code upkeep for the future. 2. Object redundancy: a. Identify all the areas wherein objects are instantiated in loop. b. Check for any business impact and remove the iteration of object creation in loops. 3. Improving Methods: a. Identify all the area where same code is used. b. For any repeating code snippets ensure that the duplicate snippet is moved to one single method for modularity. |  | Syed Farhan
US#82 | SR Description | As a CSC agent, user should be able view SR Description field (from Siebel) in SDTBooking and SDTSchedule. As a FSE, user should be able to view the SR Description field (from SDTSchedule) in SDTMobile as a message. | 1. Get the SR description field from Siebel API 2. On SDTBooking main page, SR Description should be displayed 3. SR Description field in SDTBooking should be editable 4. On SDTSchedule, SR Description (from SDTBooking) should be populated 5. As a message SR Description should be sent from SDTSchedule to SDTMobile |  | Sathyaraj Rajasekar
US#85 | ES and LS issue | As a CSC agent, user should be able to view proper ES and LS values 'when work order type is CR, Entitlement is Yes and contracts are not loaded as a part of Master Data load' so that user should be able to see the proper ES and LS values in appointment slots page. | 1. Under a scenario, when WorkOrder=CR; Entitlement=Y; and contracts are not loaded as a part of Master Data load, a. ES and LS values in SDTBooking home page should be empty or NULL b. On clicking request appointment button, appointment slots page should open c. In Appointment slots page, ES = current time+1 day and LS=current time+1days+duration d. User friendly popup/message should be displayed in case of slots unavailability. |  | Sathyaraj Rajasekar
US#81 | Activity Types filter | PROBLEM TICKET NO: PRB0045556 INCIDENT NO: 1285226 User Story: As a CSC agent, user should be restricted to launch SDTBooking application for certain WO-activity types to avoid inappropriate activity types to get invoked. | 1. SDTBooking should not be invoked for all the workorder types. User should be restricted to launch the application for certain WO types such as, a. Email activity b. Admin activity 2. SDTBooking should be launched only for the following workorder types. a. CR b. FMI c. PM d. Installation jobs e. Training f. Other(Deinstall,Move Equipment,Sales Support,Consulting) 3. For other workorder types, SDTBooking application should display an error message: "SDTBooking cannot not be launched for '@workordertype_fromSiebel' workorder" and no SDTBooking functions are allowed and SDTBooking closes. |  | Sathyaraj Rajasekar
US#25 | Part pickup - Check address enhancement - Google Map | As a CSC agent, under parts pickup grid after clicking on 'Check Address' button, user should be able to move the google map pin to tag the address in maps and save the tagged address for future use | 1. Under parts pickup grid after clicking on 'Check Address' button, google map with 'map pin' tagging to the address provided by the user should be displayed 2. User should be able to move the 'map pin' to tag the right location/improve accuracy 3. Newly tagged location should be saved for future use |  | Sathyaraj Rajasekar
US#XX | Code Optimization | <Farhan/Hita provide inputs> |  |  | Hita Soni
Note on E6: Sathyaraj Rajasekar: Various scenarios can be captured. ES and LS can be calculated accordingly
Note on C7: Sathyaraj Rajasekar: Need to rename the User Story name
Note on E7: Sathyaraj Rajasekar: Complete list of WO types to be received from Anil

## Query
# | US# | Query | Response | Raised By (Name) | Status | Open Date | Reply By (Name) | Closed Date | References | Comments
1 | US#82 | After checking in Siebel,SR Desc field is not mandatory field.Is it ok to pass blank value as desc from SDT to Click,if CSC agent does not have anything to add? |  | CG team | Open | 2017-02-07
2 | US#82 | Is that ok if we show SR desc field in the Same section where we are getting Sr No,Activity NO and service region? |  | CG team | Open | 2017-02-07
3 | US#82 | Need to confirm if SR description would be as it is that is coming from Siebel (if case is of NEW VISIT), or user should be allowed to modify the existing SR description field. If the previous SR description should be as it is, in that case we can add additional field as editable and previous SR description as read only |  | CG team | Open | 2017-02-07
4 | US#82 | What kind of validation needs to be done on/or before editing and saving the SR desc. Field ? |  | CG team | Open | 2017-02-07
5 | US#82 | To Gopi/Preeti: From Click Schedule point of view do we have any restrictions on passing the SR description ? What is the maxlength of this field? |  | CG team | Open | 2017-02-07
6 | US#85 | To Gopi/Preeti: Check on contract availability on click |  | CG team | Open | 2017-02-07
7 | US#85 | Calculation on ES & LS based on urgency of CR |  | CG team | Open | 2017-02-07
8 | US#81 | Any other activities types other than Email Outbound/admin should be shunned from using SDT ? |  | CG team | Open | 2017-02-07
9 | US#81 | Is that ok if we display an error page (with message as "Email Outbound activity is not allowed in SDT booking") in case the activity type is of EMAIL OUTBOUND, or do you need a poup for this?. As with popup, we will need to come to SDT and disable all fields and greyed out in UI. |  | CG team | Open | 2017-02-07
10 | US#81 | Need confirmation for Popup/error message for Activity type Filter. We would suggest for error message page |  | CG team | Open | 2017-02-07
11 | US#25 |  |  | CG team | Open | 2017-02-07

## Read me
Procedure to be followed for Using Query tracking Sheet
1) Projects should enter all requirements related queries in this sheet to keep all queries at one place.
2) Projects are required to send/receive updated query tracking sheet to/from client/OSC. Only the latest version of the sheet should be maintained at designated place (to avoid confusion of answers), pointed to by Projects' PML.
3) Projects should request client/OSC to enter their queries and replies also in this sheet. Even if client does not enter, Projects should keep this sheet updated.
4) The status of all pending queries should be taken in the project meetings and PSR. PL should escalate to OSC/Client for open queries.
5) Use colour code specifed for visual ease of identifying open queries.
Yellow for CLOSED queries
Grey for CANCELLED queries.
Blue for ON-HOLD queries.
No Background for Active Queries