## Sheet1
# | Test Date: | Country | FunctionModule Booking/Click | Priority | SEV | Defect Description | Status | Next Action | Owner | Comments | Raised By
1 | 2017-01-30 | PH | Booking |  |  | After launch SDT, cannot find any slot available. ES and LS same. | In Progress | RCA | Tejashree | part of All out. Needs explaination from Haritha | UAT
2 | 2017-01-30 | PH | Booking |  |  | HBS Case, After launch SDT, cannot find any slot available | Closed | RCA | Tejashree | Desired Behaviour | UAT
3 | 2017-01-30 | VN | Click |  |  | Job assigned to distant FE. | In Progress | RCA | PreetiSagar | Geocoding settings are wrongly set. Settings has to be updated for VN region. | UAT
4 | 2017-01-30 | VN | Booking |  |  | System Dependency Not working | In Progress | RCA | Jayesh/Deepak | Analysis in Progress | UAT
5 | 2017-01-30 | SG | Booking |  |  | Site and System Dependency | In Progress | RCA | Jayesh/Deepak | Analysis in Progress | UAT
6 | 2017-01-30 | PH | Booking/Click |  |  | After launch SDT, cannot find any slot available. ES and LS different. | In Progress | RCA | preetiSagar/Gopi | For Any FE Slots are available.Check Masterdata for other FE level. | UAT
7 | 2017-01-31 | VN | Click |  |  | Following error is triggering on click of “Check Address” button. “Invalid Address . Please enter correct address”. When we cross verify the below address in Google maps, It says “Unable to find”. | In Progress | RCA | PreetiSagar | It is not related to Click.Typing manual address.Solution:Updte in Siebel system or update in Trace DB and then Click. | Binu Mohan
8 | 2017-01-31 | VN | Click |  |  | removal of OLE from Click | Open | Request | Gopi |  | Binu Mohan
9 | 2017-02-01 |  | Click |  |  | message view should be removed from APAC AM/PM template on Stage env | Open | Request | Gopi |  | Paul