## Defects
# | Test Date: | Country | FunctionModule Booking/Click | Priority | Reported By | Defect Description | Status | Next Action | Owner | Comments | Defect/Enhancement
1 | 2017-01-30 | PH | Booking | SS | Rachmat | After launch SDT, cannot find any slot available. ES and LS same. | Open | Retest | SathyaRaj/Suvarna | Contract is part of fallout. 01/02: Meera to connect with Sitara. Workaround solution: Manually enter ES and LS and see able to get slots(Rachmat). Retest results: Still slots not coming. Evidence shared. 02/02: Identified master data issue. 232 sites still impacted, all PH only. Validated on geocoding, getting slots using workaround solution for the SR 1-4893684356
2 | 2017-01-30 | PH | Booking | H | Rachmat | HBS Case, After launch SDT, cannot find any slot available | Resolved | Check Required FE | Meera | Desired Behavior Anil and CM to provide explaination on current behavior on 02/02 02/02: Required FE doesn't have right skills. (Meera)
3 | 2017-01-30 | VN | Click | M | Rachmat | Job assigned to distant FE. | Open | RCA | Preeti | 01/02: Updated config for VM for geocoding in Click Stg, ready for retest. Click config changes done, issue persists.
4 | 2017-01-30 | VN | Booking | M | Rachmat | System Dependency Not working | Open | Check Prod behavior | Jayesh | Analysis in progress 02/02: Rachmat to do testing for MY.
5 | 2017-01-30 | SG | Booking | M | Rachmat | Site and System Dependency | Open | Check Prod behavior | Jayesh | Analysis in progress
6 | 2017-01-30 | PH | Booking | SS | Rachmat | After launch SDT, cannot find any slot available. ES and LS different. | Open | Retest | Tejashree | Non Issue. Getting slots for Any FE. Tejashree to share screenshots of no level 2 FE available. 2/2/2017: For Evidence email sent .As per the analysis of master data files, for skill Level 2 FEs are available in click. But travel time for those FEs is more than 3 hours which results in rule violation in click. So appointment slots are not available for skill level 2 in SDT. 02/02: Validated on geocoding, getting slots now for SR : 1-4895801631 - There are 232 PH sites currently having incorrect geocoding in Click due to bad master data.
7 | 2017-02-01 | PH | Booking | SS | Rachmat | After launch SDT, cannot find any slot | Open | Duplicate of #6 | Rachmat | For SR Number: 1-4895801631 of PH-Service region FE SSO ID is not getting pulled from Click. And also for the same region with skill level 2 FEs are available in the click. As the travel time of both of these engineers is more than 3 hours, we are not able to get the slots when we launch the SDT application 02/02: Retest results should pass now for this particular SR/System.
8 | 2017-01-30 | ID | Booking | L | Sitara | Slots for Jayapura time zone | Open | RCA | Farhaan | 01/02- Leslie to share sysId/SR for Jayapura. [Complete] Analyze the reasoning of non availability of slots.
9 | 2017-01-31 | VN | Click | SS | Sitara | NA for Vietnam(Geocoding) | Open | Retest | Gopi | Retesting in stage.
10 | 2017-01-30 |  | Click | M | Meera | OLE Removal for ASEAN | Open | Remove OLEs | Preeti | Refer fallouts on GE Box posted on 31st Jan and provide confirmation on what FE to be removed Meera: Checked and email sent to Rahul for confirmation on 1 PH FE. 02/02: Remove OLEs from stage
11 | 2017-01-31 | SG | Booking | M | Kannan | When we tried to add a part pickup job with a Singapore address taken from the Site master file, Following error is triggering on click of “Check Address” button. “Invalid Address . Please enter correct address”. When we cross verified the address in Google maps, It says “Unable to find”. (Address tested are mentioned in the attachment) | Open | RCA | Ebaad/Deepak | 2/2/2017:We need to update the address of the site which is a valid one. The same address should be updated in click and siebel system. Business has to update the address
12 | 2017-02-02 | VN | Booking | L | Rachmat | Error message: Invalid addrees when checking address for creating part pick up jobs. This error happened both for GE Ho Chi Minh and Hanoi office | Open | RCA | Prajna
13 | 2017-02-02 | PH | Booking | L | Rachmat | Got available slots after requested extended slot. Can find the address when creating part pick job however, error message: “Error occurs while creating the task! (Exception: The input for database column “Streets” is longer than the column’s maximum length which is 64" when creating the task | Open | RCA | Tejashree
12 | 2017-02-01 | PH | Booking | L |  | When we tried to add a “Customer Site” part pickup job, The field “Address” is auto-populated with the address exist in Siebel, but when we click on the “Check Address” button, SDT Booking Google map is showing different address. The Siebel ‘Ship to Address’ field and SDT Booking ‘Part Tool Details’ section’s ‘Address’ field has the same address, but the ‘Google Map of SDT Booking’ is showing different location. (Address and SR mentioned in screenshot) | Open | RCA | Ebaad/Deepak

## Enhancements
# | Test Date: | Country | FunctionModule Booking/Click | Priority | SEV | Defect Description | Status | Next Action | Owner | Comments
1 | 2017-01-30 | PH | Booking | 1 |  | After launch SDT, cannot find any slot available. ES and LS same. | Open | RCA | Meera/Rachmat | Meera to connect with Sitara. Workaround solution: Manually enter ES and LS and see able to get slots. contract is part of fallout, enhance the application to handle this scenario, need a user story.