## Sheet1 (hidden)
Name(s) | Available Days during Sprint | Leaves(Sick,OOO,Vacation,Training) | Available Hrs per Day | Total Available Hrs per Sprint | Hours Spent on Sprint Ceromonies | Ge meetings/Emails | Support | Total Available Hours | Hours spent on tasks | Resource Utilization (in %) | Notes
Hita Soni | 10 | 1 | 8 | 72 | 13.05 | 13.5 |  | 45.45 | 45.45 | 100
Farhan Hussain | 10 | 1 | 8 | 72 | 13.05 | 13.5 |  | 45.45 | 45.45 | 100
Tejashree Bhagat | 10 | 2 | 8 | 64 | 11.6 | 12 |  | 40.4 | 40.4 | 100 | 10th March 2017 -Leave plan
Jayesh Soni | 10 | 5 | 8 | 40 | 7.25 | 7.5 | 12 | 13.25 | 13.25 | 100 | Leave Plan- 3/14/2017-3/17/2017
Ebaad Chowdhry | 10 | 1 | 8 | 72 | 13.05 | 13.5 |  | 45.45 | 45.45 | 100
Deepak Vishwakarma | 10 | 5 | 8 | 40 | 7.25 | 7.5 | 12 | 13.25 | 13.25 | 100 | Leave Plan- 3/14/2017-3/17/2017
Prajna Monappa | 10 |  | 8 | 80 | 14.5 | 15 |  | 50.5 | 50.5 | 100
Sathyaraj Rajasekar | 10 |  | 8 | 80 | 14.5 | 15 | 20 | 30.5 | 30.5 | 100
Binu Mohan | 10 |  | 8 | 80 | 14.5 | 15 |  | 50.5 | 50.5 | 100
Ramesh, Dhivyabharathi | 10 |  | 8 | 80 | 14.5 | 15 |  | 50.5 | 50.5 | 100
Gopi Mottai | 10 |  | 8 | 80 | 14.5 | 15 | 50 | 0.5 | 0.5 | 100 | He will be working on Support & Mobile Sync issues.
PreetiSagar Godi | 10 |  | 8 | 80 | 14.5 | 15 | 40 | 10.5 | 10.5 | 100 | He will be working on Support & Mobile Sync issues.
Saraswathi Nagaraj | 10 | 1 | 8 | 72 | 13.05 | 13.5 |  | 45.45 | 45.45 | 100 | Project Management related activities
Suvarna Dmello | 10 | 2 | 8 | 64 | 11.6 | 12 |  | 40.4 | 40.4 | 100 | 10th March 2017 -Leave plan, Working on Scrum Ceremonies,Impedements for the team
Row Labels | Sum of Total Available Hrs per Sprint | Sum of Hours Spent on Sprint Ceromonies | Sum of Ge meetings/Emails | Sum of Total Available Hours | Sum of Hours spent on tasks | Count of Support | Sum of Resource Utilization (in %)
Binu Mohan | 80 | 14.5 | 15 | 50.5 | 50.5 |  | 100
Deepak Vishwakarma | 40 | 7.25 | 7.5 | 13.25 | 13.25 | 1 | 100
Ebaad Chowdhry | 72 | 13.05 | 13.5 | 45.45 | 45.45 |  | 100
Farhan Hussain | 72 | 13.05 | 13.5 | 45.45 | 45.45 |  | 100
Gopi Mottai | 80 | 14.5 | 15 | 0.5 | 0.5 | 1 | 100
Hita Soni | 72 | 13.05 | 13.5 | 45.45 | 45.45 |  | 100
Jayesh Soni | 40 | 7.25 | 7.5 | 13.25 | 13.25 | 1 | 100
Prajna Monappa | 80 | 14.5 | 15 | 50.5 | 50.5 |  | 100
PreetiSagar Godi | 80 | 14.5 | 15 | 10.5 | 10.5 | 1 | 100
Ramesh, Dhivyabharathi | 80 | 14.5 | 15 | 50.5 | 50.5 |  | 100
Saraswathi Nagaraj | 72 | 13.05 | 13.5 | 45.45 | 45.45 |  | 100
Sathyaraj Rajasekar | 80 | 14.5 | 15 | 30.5 | 30.5 | 1 | 100
Suvarna Dmello | 64 | 11.6 | 12 | 40.4 | 40.4 |  | 100
Tejashree Bhagat | 64 | 11.6 | 12 | 40.4 | 40.4 |  | 100
Grand Total | 976 | 176.9 | 183 | 482.1 | 482.1 | 5 | 1400

## Velocity (hidden)
Sprint | Velocity | No of days | Accepted By PO
Support Iteration 1(02/01/2017 - 02/10/2017) | 5 | 8 | 5
Support Iteration 2( 2/13/2017 - 2/28/2017) | 20 | 12 | 19
Support Iteration 3(03/01/2017 - 03/15/2017) | 20 | 11 | 20
Support Iteration 4 | 4 | 3 | 4
Sprint | Velocity | No of days
SDT Iteration 1(02/14/2017 - 02/27/2017) | 50 | 10 |  | Row Labels | Sum of Velocity | Sum of No of days
SDT Iteration 2(03/06/2017 - 03/10/2017) | 9 | 5 |  | SDT Iteration 1(02/14/2017 - 02/27/2017) | 50 | 10
|  |  |  | SDT Iteration 2(03/06/2017 - 03/10/2017) | 9 | 5
|  |  |  | Grand Total | 59 | 15

## ResUtilization(Mar20 -Mar 24) (hidden)
Name(s) | Available Days during Sprint | Leaves(Sick,OOO,Vacation,Training) | Available Hrs per Day | Total Available Hrs per Sprint | Hours Spent on Sprint Ceromonies | Ge meetings/Emails | Support | Total Available Hours | Hours spent on tasks | Resource Utilization (in %) | Notes
Hita Soni | 5 |  | 8 | 40 | 7.25 | 15 |  | 17.75 | 17.75 | 100
Farhan Hussain | 5 |  | 8 | 40 | 7.25 | 15 |  | 17.75 | 17.75 | 100
Tejashree Bhagat | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 27.75 | 100
Jayesh Soni | 5 |  | 8 | 40 | 7.25 | 5 | 5 | 22.75 | 22.75 | 100
Ebaad Chowdhry | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 27.75 | 100
Deepak Vishwakarma | 5 |  | 8 | 40 | 7.25 | 5 | 5 | 22.75 | 22.75 | 100
Prajna Monappa | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 27.75 | 100
Sathyaraj Rajasekar | 5 |  | 8 | 40 | 7.25 | 15 | 10 | 7.75 | 7.75 | 100
Binu Mohan | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 27.75 | 100
Ramesh, Dhivyabharathi | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 27.75 | 100
Gopi Mottai | 5 |  | 8 | 40 | 7.25 | 25 | 10 | -2.25 | -2.25 | 100
PreetiSagar Godi | 5 |  | 8 | 40 | 7.25 | 25 | 10 | -2.25 | -2.25 | 100
Saraswathi Nagaraj | 5 |  | 8 | 40 | 7.25 | 7.5 |  |  | 0 | 271.1864 | Project Management related activities
Suvarna Dmello | 5 |  | 8 | 40 | 7.25 | 15 |  | 17.75 | 17.75 | 100 | 10th March 2017 -Leave plan, Working on Scrum Ceremonies,Impedements for the team
Urmila Gumata | 5 |  | 8 | 40 | 7.25 | 15 |  | 17.75 | 17.75 | 100
Name(s) | Available Days during Sprint | Leaves(Sick,OOO,Vacation,Training) | Available Hrs per Day | Total Available Hrs per Sprint | Hours Spent on Sprint Ceromonies | Ge meetings/Emails | Support | Total Available Hours | Hours Scheduled (spent on tasks) | Resource Utilization (in %) | Notes
Hita Soni | 5 |  | 8 | 40 | 7.25 | 15 |  | 17.75 | 13 | 88.125 | Understanding the requirement on SDT Instance realignment for configuring SB1 and Sb3 code. SDT CAST Results discussion. Followup on SDT known defects in team. Analysis document review for Index creation. Code integration for TimeZone conversion calls changes. (Today or tomorrow) Andrey's performance assessment call
Farhan Hussain | 5 |  | 8 | 40 | 7.25 | 15 |  | 17.75 | 12 | 85.625 | code review,Implementation of click calls,POC on Logging
Tejashree Bhagat | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 15 | 68.125 | logging tool analysis
Jayesh Soni | 5 |  | 8 | 40 | 7.25 | 5 | 7.5 | 20.25 | 11 | 76.875 | logging tool analysis
Ebaad Chowdhry | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 21 | 83.125 | google call(8hrs),Incident analysis(1),doc(4),IP address(3),SB3 analysis(5)
Deepak Vishwakarma | 5 |  | 8 | 40 | 7.25 | 5 | 10 | 17.75 | 9 | 78.125
Prajna Monappa | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 15 | 68.125 | US155 ,
Sathyaraj Rajasekar | 5 |  | 8 | 40 | 7.25 | 15 | 10 | 7.75 | 2 | 85.625 | Incident calls and alignment(5)
Gopi Mottai | 5 |  | 8 | 40 | 7.25 | 20 | 8 | 4.75 |  | 88.125
PreetiSagar Godi | 5 |  | 8 | 40 | 7.25 | 20 | 5 | 7.75 | 2 | 85.625
Saraswathi Nagaraj | 5 |  | 8 | 40 | 7.25 | 7.5 |  |  |  | 36.875 | Project Management related activities
Suvarna Dmello | 5 |  | 8 | 40 | 7.25 | 15 | 8 | 9.75 | 4 | 85.625 | Working on Scrum Ceremonies,Impedements for the team,User Stories,Andrey performance calls
Urmila Gumata | 5 |  | 8 | 40 | 7.25 | 15 |  | 17.75 | 10 | 80.625 | US174,indexing follwup,Andrey performance call,Winscp S/W,ANZ requirement discussion
Binu Mohan | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 12 | 60.625 | 1. Manually check performance of all business scenarios in STG and CRP. To test the performance using JMeter
Ramesh, Dhivyabharathi | 5 |  | 8 | 40 | 7.25 | 5 |  | 27.75 | 11 | 58.125 | 1. Manually check performance of all business scenarios in STG and CRP. To test the performance using JMeter
Row Labels | Sum of Available Hrs per Day | Sum of Total Available Hrs per Sprint | Sum of Hours Spent on Sprint Ceromonies | Sum of Ge meetings/Emails | Sum of Resource Utilization (in %)
Binu Mohan | 8 | 40 | 7.25 | 5 | 60.625
(blank) | 8 | 40 | 7.25 | 5 | 60.625
(blank) | 8 | 40 | 7.25 | 5 | 60.625
12 | 8 | 40 | 7.25 | 5 | 60.625
Deepak Vishwakarma | 8 | 40 | 7.25 | 5 | 78.125
(blank) | 8 | 40 | 7.25 | 5 | 78.125
10 | 8 | 40 | 7.25 | 5 | 78.125
9 | 8 | 40 | 7.25 | 5 | 78.125
Ebaad Chowdhry | 8 | 40 | 7.25 | 5 | 83.125
(blank) | 8 | 40 | 7.25 | 5 | 83.125
(blank) | 8 | 40 | 7.25 | 5 | 83.125
21 | 8 | 40 | 7.25 | 5 | 83.125
Farhan Hussain | 8 | 40 | 7.25 | 15 | 85.625
(blank) | 8 | 40 | 7.25 | 15 | 85.625
(blank) | 8 | 40 | 7.25 | 15 | 85.625
12 | 8 | 40 | 7.25 | 15 | 85.625
Gopi Mottai | 8 | 40 | 7.25 | 20 | 88.125
(blank) | 8 | 40 | 7.25 | 20 | 88.125
8 | 8 | 40 | 7.25 | 20 | 88.125
(blank) | 8 | 40 | 7.25 | 20 | 88.125
Hita Soni | 8 | 40 | 7.25 | 15 | 88.125
(blank) | 8 | 40 | 7.25 | 15 | 88.125
(blank) | 8 | 40 | 7.25 | 15 | 88.125
13 | 8 | 40 | 7.25 | 15 | 88.125
Jayesh Soni | 8 | 40 | 7.25 | 5 | 76.875
(blank) | 8 | 40 | 7.25 | 5 | 76.875
7.5 | 8 | 40 | 7.25 | 5 | 76.875
11 | 8 | 40 | 7.25 | 5 | 76.875
Prajna Monappa | 8 | 40 | 7.25 | 5 | 68.125
(blank) | 8 | 40 | 7.25 | 5 | 68.125
(blank) | 8 | 40 | 7.25 | 5 | 68.125
15 | 8 | 40 | 7.25 | 5 | 68.125
PreetiSagar Godi | 8 | 40 | 7.25 | 20 | 85.625
(blank) | 8 | 40 | 7.25 | 20 | 85.625
5 | 8 | 40 | 7.25 | 20 | 85.625
2 | 8 | 40 | 7.25 | 20 | 85.625
Ramesh, Dhivyabharathi | 8 | 40 | 7.25 | 5 | 58.125
(blank) | 8 | 40 | 7.25 | 5 | 58.125
(blank) | 8 | 40 | 7.25 | 5 | 58.125
11 | 8 | 40 | 7.25 | 5 | 58.125
Saraswathi Nagaraj | 8 | 40 | 7.25 | 7.5 | 36.875
(blank) | 8 | 40 | 7.25 | 7.5 | 36.875
(blank) | 8 | 40 | 7.25 | 7.5 | 36.875
(blank) | 8 | 40 | 7.25 | 7.5 | 36.875
Sathyaraj Rajasekar | 8 | 40 | 7.25 | 15 | 80.625
(blank) | 8 | 40 | 7.25 | 15 | 80.625
10 | 8 | 40 | 7.25 | 15 | 80.625
(blank) | 8 | 40 | 7.25 | 15 | 80.625
Suvarna Dmello | 8 | 40 | 7.25 | 15 | 80.625
(blank) | 8 | 40 | 7.25 | 15 | 80.625
5 | 8 | 40 | 7.25 | 15 | 80.625
5 | 8 | 40 | 7.25 | 15 | 80.625
Tejashree Bhagat | 8 | 40 | 7.25 | 5 | 68.125
(blank) | 8 | 40 | 7.25 | 5 | 68.125
(blank) | 8 | 40 | 7.25 | 5 | 68.125
15 | 8 | 40 | 7.25 | 5 | 68.125
Urmila Gumata | 8 | 40 | 7.25 | 15 | 80.625
(blank) | 8 | 40 | 7.25 | 15 | 80.625
(blank) | 8 | 40 | 7.25 | 15 | 80.625
10 | 8 | 40 | 7.25 | 15 | 80.625
Grand Total | 120 | 600 | 108.75 | 157.5 | 1119.375

## Velocity 3-22-17 (hidden)
Sprint | Velocity(Story Points) | Accepted By PO(SPs) | No of days
Support Iteration 1(02/01/2017 - 02/10/2017) | 5 | 5 | 8
Support Iteration 2( 2/13/2017 - 2/28/2017) | 20 | 19 | 12
Support Iteration 3(03/01/2017 - 03/15/2017) | 20 | 20 | 11
Sprint | Velocity(Story Points) | Accepted By PO(SPs) | No of days
SDT Iteration 1(02/14/2017 - 02/27/2017) | 50 | 13 | 10
SDT Iteration 2(03/06/2017 - 03/10/2017) | 9 | 9 | 5

## User Stories
Sr No | US# | US Title | Release | Iteration | Comments
Non -Functional Requirements
1 | US87 | TECH - Code Optimization -Phase1 |  | SDT Iteration 1 - (02/14/2017 - 02/27/2017)
2 | US154 | TECH - Minimize internal calls in ClickCallByOperation method | Release 2 (Q2'17) | SDT Iteration 3 -(03/21/2017 -03/31/2017)
3 | US134 | TECH - Minimizing Time Zone conversion calls | Release 2 (Q2'17) | SDT Iteration 3 -(03/21/2017 -03/31/2017)
4 | US155 | TECH - SR Data retrieval - Implementation | Release 2 (Q2'17) | SDT Iteration 4 | Dependancy on click & Siebel
5 | US156 | TECH - Indexing Mechanisum in Click-Implementation | Release 2 (Q2'17) | SDT Iteration 3 -(03/21/2017 -03/31/2017)
6 | US108 | TECH SPIKE - Architecture assessment -Analysis | NA | SDT Iteration 1 - (02/14/2017 - 02/27/2017)
7 | US98 | SPIKE - Landing page optimization - Analysis | NA | SDT Iteration 1 - (02/14/2017 - 02/27/2017)
8 | US100 | SPIKE - Session Optimization-Analysis | NA | SDT Iteration 1 - (02/14/2017 - 02/27/2017)
9 | US119 | SPIKE - Indexing Mechanisum in Click-Analysis | NA | SDT Iteration 2 - (03/06/2017 - 03/10/2017)
10 | US131 | TECH -SPIKE - SR Data retrieval - Analysis | NA | SDT Iteration 2 - (03/06/2017 - 03/10/2017)
11 | US133 | TECH - SPIKE - Click Calls - Analysis | NA | SDT Iteration 2 - (03/06/2017 - 03/10/2017)
12 | US174 | TECH- SPIKE- Filter the no. of tasks obtained in the method GetTasksRequestByPropertyName | NA | SDT Iteration 3 -(03/21/2017 -03/31/2017)
| US184 | TECH - Logging Mechanisum
13 | US97 | TECH - Improving Logging Mechanism - Phase 1 | Release 1.3.1 | SDT Iteration 1 - (02/14/2017 - 02/27/2017)
14 | US185 | TECH - Improving Logging Mechanism - Phase 2 | Release 2 (Q2'17)
| US115 | SPIKE - Use local database for optimizing click calls - POC |  |  | waiting for Urmila
15 | US125 | List the frequently used tables and Create Schema.
16 | US130 | Creation Of Scripts
17 | US126 | Dot Net code to retrieve data from Click DB and insert into SQL DB
18 | US127 | Create Task Scheduler
19 | US128 | Analyse SDT Application to make changes to fetch data from the local DB.
20 | US129 | Implementation
Functional Requirements
21 | US149 | FMI Logic modification -Middleware | Release 2 (Q2'17) | SDT Iteration 3 -(03/21/2017 -03/31/2017)
22 | US81 | Activity Types filter |  |  | remove this US from Rally
23 | US85 | ES & LS Same | Release 1.3.1 | SDT Iteration 1 - (02/14/2017 - 02/27/2017)
24 | US28 | Multi Man Task - SDT Booking | Release 3 (Q3'17)
25 | US70 | Replace Google Maps API to Google Places to Capture address. | Release 1.3 | SDT Iteration 1a -Release 1.3
26 | US82 | SR Description | Release 2 (Q2'17) | SDT Iteration 4 | Dependancy on click
27 | US25 | SPIKE -Part pick up - Check Address enhancement - Google map | Release 3 (Q3'17)
28 | US177 | Known Defect -Some of the Extended slots doesn't have SLA details. | Release 2 (Q2'17)
29 | US178 | Known Defect - When clicking on the Request Appointment button, Getting the Error message as expected â€œContracts are not loaded in click . | Release 2 (Q2'17)
30 | US179 | Known Defect - Appointment slots are before Early Startâ€ (Selected ES as 15-03-2017 but getting slots for 14-03-2017). | Release 2 (Q2'17)
31 | US180 | Format of Early Start and Late Startâ€ are not in sink when it displays on the bottom of the request appointment grid. (ES is in DD/MM/YYYY and LS is in MM/DD/YYYY) | Release 2 (Q2'17)
32 | US186 | If SiteID is NULL, please display as Task cannot be created because SiteID is NULL | Release 2 (Q2'17)
33 | US187 | Known Defect - Issue 2: When a contract does not exist in CLICK, we still display “From Contract”. Do evaluate the option to remove the text, give a pop-up message and follow the workflow for no contracts. | Release 2 (Q2'17)
ANZ requirements
| US165 | ANZ -SDT
33 | US175 | SPIKE SDT & WebClient -Accurate error messages | NA | SDT Iteration 3 -(03/21/2017 -03/31/2017)
34 | US138 | ANZ- SDT - System response time | Release 3 (Q3'17)
35 | US139 | ANZ - SDT & WebClient -Accurate error messages | Release 3 (Q3'17)
36 | US140 | ANZ - SDT -Part tracking # integration | Release 3 (Q3'17)

## Release plan
Sr No | Activity Details | Start Date | End Date
1 | Release 2 (Q2'17) | 2017-03-01 | 2017-05-31
2 | SDT Iteration 3 -(03/21/2017 -03/31/2017) | 2017-03-21 | 2017-03-31
3 | SDT Iteration 4 -(04/01/2017 -04/14/2017) | 2017-04-01 | 2017-04-14
4 | Deployment & testing In CRP (SDT Iteration 3)
5 | Deployment In Staging & Testing
6 | UAT testing