## Sheet1
Sr. No. | Release | User Story# | Resource | File Name | File path | Method name | Class name | Description of changes | Comments | Status
1 | R1.4 | TA900 | Tejashree | HomeController.cs | NewSDTApplication\Controllers\HomeController.cs | Index() GetSiteSytemClickTaskCount() GetFSE1ddlItems() | HomeController | Removed the commented code |  | Completed
2 | R1.4 | TA900 | Tejashree | RequestAppointmentBookingController.cs | NewSDTApplication\Controllers\RequestAppointmentBookingController.cs | GetAppointments() RequestAppointment() RequestAppointment() RequestExtendedSlotsTask() ProcessTsk() ProcessTaskwithoutAppointment() ModifyVisit GetSlotDetails() | RequestAppointmentBookingController | Removed the commented code |  | Completed
3 | R1.4 | TA900 | Tejashree | SiteController.cs | NewSDTApplication\Controllers\SiteController.cs | CreateVisitWithDependencies() SiteDependencies() GetSiteDependencies() | SiteController | Removed the commented code |  | Completed
4 | R1.4 | TA900 | Tejashree | SystemController.cs | NewSDTApplication\Controllers\SystemController.cs | SystemDependencies() GetSystemDependencies() GetActualSystemDependencies() CreateVisitWithDependencies() | SystemController | Removed the commented code |  | Completed
5 | R1.4 | TA900 | Tejashree | AppointmentSlots.cs | NewSDTApplication\Models\AppointmentSlots.cs |  | AppointmentSlots | Removed the commented code |  | Completed
6 | R1.4 | TA900 | Tejashree | CustomTasksList.cs | NewSDTApplication\Models\CustomTasksList.cs |  | DependencyTasksList | Removed the commented code |  | Completed
7 | R1.4 | TA900 | Tejashree | SiebelJsonToEntity.cs | NewSDTApplication\Models\SiebelJsonToEntity.cs |  | ServiceRequest | Removed the commented code |  | Completed
8 | R1.4 | TA900 | Tejashree | TaskAssignmentRequestedProperties.cs | NewSDTApplication\Models\TaskAssignmentRequestedProperties.cs |  | TaskRequestedProperties | Removed the commented code |  | Completed
9 | R1.4 | TA900 | Tejashree | CustomValidation.js | NewSDTApplication\Scripts\CustomValidation.js | $(document).ready(function () $("#btnrequestappointment").click(function $("#taskduration").change(function () $("#taskhrs").change(function () $("#ClosedDiv").click(function () $('#btnPotentialDependencySite').click(function () $('#btnActualDependencySite').click(function () $('#btnPotentialDependencySystem').click(function () $('#btnActualDependencySystem').click(function () ModifyMainAndPartValidations() $("#modifyTaskModel").click(function $("#modVis").click(function (e) $("#btnCancelTask").click(function $("#canclTaskModel").click(function $("#canclPTaskModel").click(function $("#modifytask").click(function $("#creVisNA").click(function $("#txtlstart").keyup(function $("#txtestart").keyup(function EarlyStartAndLateStartValidations() taskDatetimeValidations() $("#cancltask").click(function DeliveryDateValidations() ValidateSSOid(element) $(function ($) |  | Removed the commented code |  | Completed
10 | R1.4 | TA900 | Tejashree | GoogleMapUtil.js | NewSDTApplication\Scripts\GoogleMapUtil.js | $(document).ready(function ValidateError(element) ValidateSucess(element) InitOldAddress() populateOldAddress AddRecord() AddOrUpdateComment AddOrUpdateComment2 DeleteRow() nextdata() AsyncConfirmYesNo() AsyncConfirmGooglemapYesNo() DeleteMarker |  | Removed the commented code |  | Completed
11 | R1.4 | TA900 | Tejashree | CallClickService.cs | NewSDTApplication\Utilities\CallClickService.cs | GetTasksRequestByPropertyName GetESLSByStandardOperation OpenConnectionToSDT CloseConnectionSDT GetTravelTimeWithKeys ClickCallToCreateTask ClickCallByOperation ModifyVisit CancelTask GetSystemDetails GetSiteDetails GetDateDetails CreateTaskWithDependencies CreateTaskWithSystemDependencies GetPriority PartPickDependency | CallClickSerrvice | Removed the commented code |  | Completed
12 | R1.4 | TA900 | Tejashree | CountriesTimeZoneConversion.cs | NewSDTApplication\Utilities\CountriesTimeZoneConversion.cs | GetTimeZone ConvertDesiredDate GoogleAddressCall GoogleAddressCallForDesiredDate | CountriesTimeZoneConversion | Removed the commented code |  | Completed
13 | R1.4 | TA900 | Tejashree | SSOLogic.cs | NewSDTApplication\Utilities\SSOLogic.cs | GetSSODetails GetValidFSESSOID | SSOLogic | Removed the commented code |  | Completed
14 | R1.4 | TA900 | Tejashree | TrasformSiebelToClick.cs | NewSDTApplication\Utilities\TrasformSiebelToClick.cs | GetXMlData() GetTaskType GetTaskSubType GetSystemStatus | TrasformSiebelToClick | Removed the commented code |  | Completed
15 | R1.4 | TA900 | Tejashree | _InstallationDispatchDetail.cshtml | NewSDTApplication\Views\Home\_InstallationDispatchDetail.cshtml | NA | NA | Removed the commented code | Commented code removed written below the line: <select class="form-control" id="Skillfse1"> Hard coded values were given as commented lines for "Any FSE" etc… | Completed
16 | R1.4 | TA900 | Tejashree | FMIView.cshtml | NewSDTApplication\Views\Home\FMIView.cshtml | NA | NA | Removed the commented code | commented FMI Type in FMI Details section removed | Completed
17 | R1.4 | TA900 | Tejashree | Index.cshtml | NewSDTApplication\Views\Home\Index.cshtml | NA | NA | Removed the commented code | Commented code removed written below the line: <select class="form-control" id="Skillfse1"> Hard coded values were given as commented lines for "Any FSE" etc… | Completed
18 | R1.4 | TA900 | Tejashree | PMView.cshtml | NewSDTApplication\Views\Home\PMView.cshtml | NA | NA | Removed the commented code | Removed commented code which was same as uncommented one | Completed
19 | R1.4 | TA900 | Tejashree | RequestAppointment.cshtml | NewSDTApplication\Views\RequestAppointmentBooking\RequestAppointment.cshtml | NA | NA | Removed the commented code | Removed commented code which was same as uncommented one | Completed
20 | R1.4 | TA900 | Tejashree | _Layout.cshtml | NewSDTApplication\Views\Shared\_Layout.cshtml | NA | NA | Removed the commented code | Removed commented code which was same as uncommented one | Completed
21 | R1.4 | TA900 | Tejashree | _LayoutError.cshtml | NewSDTApplication\Views\Shared\_LayoutError.cshtml | NA | NA | Removed the commented code | Removed commented code which was same as uncommented one | Completed
22 | R1.4 | TA900 | Tejashree | Error.cshtml | NewSDTApplication\Views\Shared\Error.cshtml | NA | NA | Removed the commented code | Removed commented code which was same as uncommented one | Completed
23 | R1.4 | TA900 | Tejashree | SiteDependencies.cshtml | NewSDTApplication\Views\Site\SiteDependencies.cshtml | NA | NA | Removed the commented code | Removed commented stylesheets | Completed
24 | R1.4 | TA900 | Tejashree | SystemDependencies.cshtml | NewSDTApplication\Views\System\SystemDependencies.cshtml | NA | NA | Removed the commented code | Removed commented stylesheets | Completed
25 | R1.4 | TA900 | Tejashree | Global.asax.cs | NewSDTApplication\Global.asax.cs | Session_End | MvcApplication | Removed the commented code |  | Completed
26 | R1.4 | TA900 | Tejashree | Authentication.cs | NewSDTApplication\App_Data\Authentication.cs | OAuthAuthentication | Program | Removed the commented code |  | Completed
27 | R.1.3.1 | US85 | Prajna | CustomValidation.js | NewSDTApplication\Scripts\CustomValidation.js | ("#btnrequestappointment").click(function(e) | NA | Changes are done according to the changes asked by Sitara. Code if written to give popup when SR=corrective repaire and Entitlement flag=Y and ES and LS is supposed to loaded from contract. | //prajna Change for US85 starts (Same ES and LS) New code added for Change asked //prajna Change for US85 ends (Same ES and LS) New code added for Change asked | Completed
28 | R.1.3.1 | US85 | Prajna |  | NewSDTApplication\Controllers\RequestAppointmentBookingController.cs | RequestAppointment() | RequestAppointmentBookingController | To check the condition for values in ES and LS | //Prajna US85 changes starts (For same ES and LS) //Prajna US85 changes ends (For same ES and LS) | Completed
29 | R2.0 | US134/TA1188 | Ebaad | HomeController.cs | NewSDTApplication\Controllers\HomeController.cs | Index | HomeController | Optimization by reduction of Google TimeZone Conversion Calls |  | Code Review- In Progress
30 | R2.0 | US134/TA1188 | Ebaad | ClickCallService.cs | NewSDTApplication\Utilities\ClickCallService.cs | CreateTaskWithSystemDependencies CreateTaskWithDependencies ClickCallByOperation | ClickCallService | Optimization by reduction of Google TimeZone Conversion Calls |  | Code Review- In Progress
31 | R2.0 | US180 | Prajna | RequestAppointmentBookingController.cs | NewSDTApplication\Controllers\RequestAppointmentBookingController.cs | RequestAppointment() | RequestAppointmentBookingController | If one of the fields(ES/LS) is blank then in the request appointment page there is no consistancy in the formate of the dates. | //Prajna US180 changes starts (For Format for ES and LS if one of them is blank) //Prajna US180 changes Ends (For Format for ES and LS if one of them is blank) | Pending for code review
32 | R2.0 | US189 | Deepak | HomeController.cs | NewSDTApplication\Controllers\HomeController.cs | Index() | HomeController | LS logic should be replaced from 7 days to 14 days | //Deepak – 23/03/2017 – US149/TaskNo#1283 - Replacing FMI days from 7 to 14 and Time-23:59 | Pending for code review
33 | R2.0 | US156 | Urmila | CallClickSerrvice.cs | NewSDTApplication\Utilities\CallClickSerrvice.cs | GetTasksRequestByPropertyName | CallClickSerrvice.cs | Implemented indexing mechanism instead of dynamic grouping to fetch tasks data from click database | 1)The code starts and ends within the below comments in the class file//US156-Implementing indexing mechanism starts // US156-Implementing indexing mechanism ends 2)Response time captured within the below comments //US156-Implementing indexing mechanism starts for performance analysis //US156-Implementing indexing mechanism ends for performance analysis | Completed
34 | R2.0 | US197 | Ebaad | RequestAppointmentBookingController.cs | NewSDTApplication\Controllers\RequestAppointmentBookingController.cs | RequestExtendedSlotsTask |  | (Commented the Bump column) | US197 - Deprecation of BumpCheck calls made during slots retrieval (Commented the Bump column) | Completed
35 | R2.0 | US197 | Ebaad | RequestAppointment.cshtml | NewSDTApplication\Views\RequestAppointmentBooking\RequestAppointment.cshtml |  |  | (Commented the iterative loop which was involved in checking the Bump Status) | US197 - Deprecation of BumpCheck calls made during slots retrieval | Completed
36 | R2.0 | US197 | Ebaad | CallClickService.cs | NewSDTApplication\Utilities\ClickCallService.cs | BumpCheck() | CallClickService | (Commented the Bump Check Code) | US197 - Deprecation of BumpCheck calls made during slots retrieval | Completed
37 | R2.0 | US180 | Prajna | RequestAppointmentBookingController.cs | NewSDTApplication\Controllers\RequestAppointmentBookingController.cs | RequestAppointment() | NA | Chabged the date format of the Estart to dd/MM/yyyy | //Code Start-Prajna - 04/06/2017 - US180/TA1308 //Code End-Prajna - 04/06/2017 - US180/TA1308 | Integrated code to GIT
38 | R2.0 | US180 | Prajna | RequestAppointmentBookingController.cs | NewSDTApplication\Controllers\RequestAppointmentBookingController.cs | RequestAppointment() | NA | Changed the format of the Latestart to dd/MM/yyyy | //Code Start-Prajna - 04/06/2017 - US180/TA1308 //Code End-Prajna - 04/06/2017 - US180/TA1308 | Integrated code to GIT
39 | R2.0 | DE169 | Prajna | RequestAppointmentBookingController.cs | NewSDTApplication\Controllers\RequestAppointmentBookingController.cs | RequestAppointment() | NA | Changed the format of the Earlystart/Latestart to dd/MM/yyyy | //Prajna -04/11/2017 - De169
40 | R2.0 | US178 | Prajna | CustomValidaion.Js | NewSDTApplication\Scripts\CustomValidation.js | $("#btnrequestappointment").click(function | NA | Added condition to display popup When any one of data in ES LS is not present. Condition to check SR=CR, Entitlement=Y And Contract is not present. | //Code Start-Prajna - 04/14/2017 - US178/TA1305 //Code End-Prajna - 04/14/2017 - US178/TA1305 | Completed
41 | R2.0 | US186 | Tejashree | CustomValidation.js | NewSDTApplication\Scripts\CustomValidation.js | url: '../RequestAppointmentBooking/ProcessTaskwithoutAppointment', | NA | Added sessionStorage to store a value to check System ID null condition. Added elseif condition to display a popup. | //Code Start - Tejashree - 13/04/2017 - Scope: US186 SystemID is NULL //Code End - Tejashree - 13/04/2017 - Scope: US186 SystemID is NULL | Completed
42 | R2.0 | US186 | Tejashree | RequestAppointment.cshtml | NewSDTApplication\Views\RequestAppointmentBooking\RequestAppointment.cshtml | url: "/RequestAppointmentBooking/ProcessTsk", | NA | Added sessionStorage to fetch a value to check System ID null condition. Added elseif condition to display a popup. | //Code Start - Tejashree - 13/04/2017 - Scope: US186 SystemID is NULL //Code End - Tejashree - 13/04/2017 - Scope: US186 SystemID is NULL | Completed
43 | R2.0 | US186 | Tejashree | SiteDependencies.cshtml | NewSDTApplication\Views\Site\SiteDependencies.cshtml | url: "/Site/CreateVisitWithDependencies" | NA | Added sessionStorage to fetch a value to check System ID null condition. Added elseif condition to display a popup. | //Code Start - Tejashree - 13/04/2017 - Scope: US186 SystemID is NULL //Code End - Tejashree - 13/04/2017 - Scope: US186 SystemID is NULL | Completed
44 | R2.0 | US177 | Prajna | RequestAppointment.cshtml | NewSDTApplication\Views\RequestAppointmentBooking\RequestAppointment.cshtml | "/RequestAppointmentBooking/RequestExtendedSlotsTask | NA | Added IN SLA to the SLA column of the ExtendedWithinESLSUI list as it was showing blank when we check for extended slots | //Code Start Prajna - 04/17/2017 - US177/TA1302 //Code End Prajna - 04/17/2017 - US177/TA1302 | Pending for Integration
45 | R2.0 | US208 | Ebaad | Index.cshtml | NewSDTApplication\Views\RequestAppointmentBooking\Index.cshtml |  |  | Added Validations for Adress field, Postal code field and City name field | //Validation of Address field of Part Tool Details - US208 - 18/4/2017 by Ebaad - Allowed a - z, A - Z, 0 - 9, '.' & ',' characters //Validation of Postal Code field of Part Tool Details - US208 - 18/4/2017 by Ebaad - Allowed only 0 - 9 numerals //Validation of City field of Part Tool Details - US208 - 18/4/2017 by Ebaad - Allowed a - z & A - Z alphabetical characters | Pending for code review
46 | R2.0 | US185 | Ebaad | RequestAppointmentBookingController.cs | NewSDTApplication\Controllers\RequestAppointmentBookingController.cs | NA | NA | Added code to inject IP to the logs and structuring added to the individual log strings | //Addition of IP address in logs - US185 - 18/4/2017 by Ebaad (This line will provide us with Client IP Address) | Pending for code review
47 | R2.0 | US185 | Ebaad | HomeController.cs | NewSDTApplication\Controllers\HomeController.cs | NA | NA | Added code to inject IP to the logs and structuring added to the individual log strings | //Addition of IP address in logs - US185 - 18/4/2017 by Ebaad (This line will provide us with Client IP Address) | Pending for code review
48 | R2.0 | US185 | Ebaad | SiteController.cs | NewSDTApplication\Controllers\SiteController.cs | NA | NA | Added code to inject IP to the logs and structuring added to the individual log strings | //Addition of IP address in logs - US185 - 18/4/2017 by Ebaad (This line will provide us with Client IP Address) | Pending for code review
49 | R2.0 | US185 | Ebaad | SystemController.cs | NewSDTApplication\Controllers\SystemController.cs | NA | NA | Added code to inject IP to the logs and structuring added to the individual log strings | //Addition of IP address in logs - US185 - 18/4/2017 by Ebaad (This line will provide us with Client IP Address) | Pending for code review
50 | R2.0 | US185 | Ebaad | ClickCallService.cs | NewSDTApplication\Utilities\ClickCallService.cs | NA | NA | Added code to inject IP to the logs and structuring added to the individual log strings | //Addition of IP address in logs - US185 - 18/4/2017 by Ebaad (This line will provide us with Client IP Address) | Pending for code review
51 | R2.0 | US185 | Ebaad | SSOLogic.cs | NewSDTApplication\Utilities\SSOLogic.cs | NA | NA | Added code to inject IP to the logs and structuring added to the individual log strings | //Addition of IP address in logs - US185 - 18/4/2017 by Ebaad (This line will provide us with Client IP Address) | Pending for code review
52 | R2.0 | US185 | Ebaad | TrasformSiebelToClick.cs | NewSDTApplication\Utilities\TrasformSiebelToClick.cs | NA | NA | Added code to inject IP to the logs and structuring added to the individual log strings | //Addition of IP address in logs - US185 - 18/4/2017 by Ebaad (This line will provide us with Client IP Address) | Pending for code review
53 | R2.0 | US185 | Ebaad | CountriesTimeZoneConversion.cs | NewSDTApplication\Utilities\CountriesTimeZoneConversion.cs | NA | NA | Added code to inject IP to the logs and structuring added to the individual log strings | //Addition of IP address in logs - US185 - 18/4/2017 by Ebaad (This line will provide us with Client IP Address) | Pending for code review
54 | R2.0 | US185 | Ebaad | SessionHandler.cs | NewSDTApplication\Utilities\SessionHandler.cs | NA | NA | Added code to inject IP to the logs and structuring added to the individual log strings | //Addition of IP address in logs - US185 - 18/4/2017 by Ebaad (This line will provide us with Client IP Address) | Pending for code review
55 | R2.0 | US187 | Prajna | HomeController.cs | NewSDTApplication\Controllers\HomeController.cs | Index | HomeController | Added code to remove "*From Contract Label" when Contract is not present in Click. Also Commented existing code. | //Code Start-Prajna - 18/04/2017 - US187/TA1417 //When contract is not present in click "*From contract" Label is not displayed in Home page /Code Comment starts by Prajna for US187/TA1417-18/04/2017 | Pending for code review
56 | R2.0 | DE171 | Urmila | ClickCallService.cs | NewSDTApplication\Utilities\ClickCallService.cs | GetTasksRequestByPropertyName | CallClickService | Added code to use dynamic grouping instaed of index when system id is null | Code is an if condition with the comment: //DE171 Code-using dynamic grouping instead of indexing when system id is null/empty to avoid code exceptions | Pending for code review
57 | R2.0 | US139 | Ebaad | HomeController.cs | NewSDTApplication\Controllers\HomeController.cs | NA | NA | Added Modified error messages to the Blue screen error page |  | Pending for code review
58 | R2.0 | US139 | Ebaad | RequestAppointment.cshtml | NewSDTApplication\Views\RequestAppointmentBooking\RequestAppointment.cshtml | NA | NA | Added Jquery for more details container and Added the Model for Pop-up |  | Pending for code review
59 | R2.0 | US139 | Ebaad | SiteDependencies.cshtml | NewSDTApplication\Views\Site\SiteDependencies.cshtml | NA | NA | Added Jquery for more details container and Added the Model for Pop-up |  | Pending for code review
60 | R2.0 | US139 | Ebaad | SystemDependencies.cshtml | NewSDTApplication\Views\Site\SystemDependencies.cshtml | NA | NA | Added Jquery for more details container and Added the Model for Pop-up |  | Pending for code review
61 | R2.0 | US139 | Ebaad | CustomValidaion.Js | NewSDTApplication\Scripts\CustomValidation.js | NA | NA | Added Jquery for more details container and Added the Model for Pop-up |  | Pending for code review
62 | R2.0 | US139 | Ebaad | Custom.css | NewSDTApplication\Content\css\custom.css | NA | NA | Added style for the container for displaying more details |  | Pending for code review
63 | R2.0 | US139 | Ebaad | Index.cshtml | NewSDTApplication\Views\RequestAppointmentBooking\Index.cshtml | NA | NA | Added Jquery for more details container and Added the Model for Pop-up |  | Pending for code review
64 | R2.0 | US204 | Urmila/ Tejashree | CallClickService.cs | NewSDTApplication\Utilities\ClickCallService.cs | GetContractDetails() | CallClickSerrvice | Added new method GetContractDetails() to fetch contract detatils from Click. | //Code Start - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue //Code End - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue | Completed
65 | R2.0 | US204 | Urmila/ Tejashree | HomeController.cs | NewSDTApplication\Controllers\HomeController.cs | Index() | HomeController | Added code to make a call to function GetContractDetails() and based on the object value Session value is set. | //Code Start - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue //Code End - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue | Completed
66 | R2.0 | US204 | Urmila/ Tejashree | Index.cshtm | NewSDTApplication\Views\Home\Index.cshtml | NA | NA | Added a new hidden field. | //Code Start - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue //Code End - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue | Completed
67 | R2.0 | US204 | Urmila/ Tejashree | SiebelJsonToEntity.cs | NewSDTApplication\Models\SiebelJsonToEntity.cs | NA | ServiceRequest | Uncommented property 'openedDate' which was commented for US 87. | //Code Start - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue //Code End - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue | Completed
68 | R2.0 | US204 | Urmila/ Tejashree | CustomValidation.js | NewSDTApplication\Scripts\CustomValidation.js | NA | NA | Added validation to display popup. | //Code Start - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue //Code End - Tejashree - 07/04/2017 - Scope: US210 Contract Popup Issue | Completed
Note on K1: Soni Hita: In Progress Completed