## 31-Mar-2017
# | Rally Defect# | Date Raised: | Country | FunctionModule Booking/Click | Defect Description | Status | Raised by | Resolved by | Resolved on
DE_1.0 |  | 2017-03-31 | SDT regions | Booking | SR No.: 1-4985100636 Activity Number:1-2AG009U Ship to Site:2741244 System ID:834030032 Unable to create Visits through “Without Appointment” option for any of the SRs which we tried. Getting the below error, “Error occurs while creating the Task! (Exception:Object reference not set to an instance of an object.)” | Closed | Binu | Deepak | 2017-03-31
DE_1.1 |  | 2017-03-31 | SDT regions | Booking | SR No.: 1-4985100636 Appointment slots are not retrieving for any of the service requests. | Closed | Binu | Deepak | 2017-03-31
DE_1.2 |  | 2017-03-31 | SDT regions | Booking | SR No.: 1-4985100636 Receiving different errors whenever trying to navigate to SDT Booking Homepage from Request Appointment page by clicking on ‘SDT Booking’ hyperlink. | Closed | Dhivya | Deepak | 2017-03-31
DE_1.3 |  | 2017-03-31 | SDT regions | Booking | SR No.: 1-5035104367 Activity Number:1-2B9RREN Ship to Site: 2418340 System ID:847270001 Unable to create Same site/system dependency visits. Getting code level error. | Closed | Dhivya | Deepak | 2017-03-31
DE_1.4 |  | 2017-04-04 | SDT regions | Booking | SR: 1-5230074181 Activity: 1-2EHUN2I If Desired Date exist in Siebel for 'PM' SR type, getting wrong Early Start value and Same asset region time displaying for both ES & LS. | Closed | Dhivya | Deepak | 6th Apr
DE_1.5 | DE166 | 2017-04-07 | SDT regions | Booking | SR: 1-5320203706 Activity: 1-2FZIFGG The red icon in the 'System' button is displayed with value "28446" and when clicking on the red icon, 'Potential system dependencies' window is not showing any rows. | Open | Binu | Prajna/Deepak
DE_1.6 | DE167 | 2017-04-07 | SDT regions | Booking | SR: 1-4659530005 Activity: 1-25236KV Launched SDT Booking with the SR and added "Customer Site" part pickup, Then added "Warehouse" address and filled all the part pickup section with invalid data and clicked on "Check Address", Still able to launch map canvas and it is showing some random address for "Warehouse" in maps. | Known Defect | Binu | Ebaad
DE_1.7 | DE168 | 2017-04-11 | SDT regions | Booking | SR: 1-5545708406 Activity: 1-2JPRRZW In CRP Env, SDT Booking is getting closed when clicking on OK button of System ID null in Siebel 'Alert' popup. | Closed | Binu | Tejashree | 2017-04-19
DE_1.8 | DE169 | 2017-04-11 | SDT regions | Booking | SR: 1-5545707439 Activity: 1-2JPRR90 Type: CR Entitled Selected "ES" field value as "12/04/2017 16:17" and left "LS" as Blank and Clicked on [Request Appointment] button, in the Request Appointment grid the date for "ES" field is displayed as "12/04/2017 16:17" and for "LS" field it is displayed as "11/04/2017 20:18:00"(timestamp dispalyed with HH:MM:SS) The same behavior exist when selected "LS" field value and left "ES" as Blank. | Closed | Dhivya | Prajna | 2017-04-19
DE_1.9 | DE172 | 2017-04-19 | SDT regions | Booking | SR : 1-2982692742 Activity: 1-1DBIWCT Site: 2415767 System Id is doesn’t exist in Siebel for this SR but throwing error ‘Site ID doesn’t exist in CLICK’ when launching SDT from local env. And Getting error “Task cannot be created because SystemID is NULL” when clicking on “Create Visit Without Appnmnt” button. Attached the screenshots in Rally. | Closed | Binu | Tejashree | 2017-04-24
DE_2.0 | DE173 | 2017-04-20 | SDT regions | Booking | SR : 1-5576039794 SID: 0850450021AW2 Site : 852223 Act : 1-2K7TVUG In Local env, Unable to open the SDT Booking when Desired Date is filled in Siebel for PM SRs. Throwing the below error, "The server encountered an network error and was unable to complete your request. Please contact the Application administrator and inform them of the time the error occurred along with the error screenshot.String was not recognized as a valid DateTime" | Open | Binu
DE_2.1 | DE174 | 2017-04-24 | SDT regions | Booking | Request Appointment and Create Visit Without Appointment functionalities are not working when the following sequence of characters present in ‘SR Description’ field of SDT Booking, An alphabet enclosed in angular brackets. Eg: <p> | Open | Binu
DE_2.2 | DE174 | 2017-04-24 | SDT regions | Booking | Tooltip for ‘City’ field is showing ‘Address can only contain A-Z & a-z’ instead of ‘City can only contain A-Z & a-z’. | Open | Binu